## CPs
| CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Current Status | Status Changed in the last month | Date Issued to Ofgem | Original Expected Decision Date | Latest Expected Decision Date
STATUS - INITIAL ASSESSMENT
N/A
STATUS - DEFINITION
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Andrew Malley | 14/04/2021 | 17 | Yes - See comments in status column | TBC | The Working Group met on 02 October to review the need for a BSC change. It was agreed that a BSC change was required and that DCP 388 couldn’t be progressed until the BSC modification had been defined so DCP 388 has been paused until the Proposer raises the required BSC modification.
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | This change seeks to ensure that all DCUSA Parties, that de-energise metering equipment as part of any planned work, provide the Distributor with advance notification of the supply interruption. | General | 1 | Melissa Kendal / Richard Colwill | TBC | 2023-03-06 | 15 | No | Next scheduled release following approval | This CP is on hold pending confirmation from the Proposer as to whether they wish to continue to progress DCP 419 following Ofgem's decision on the related REC change. | #REF!
DCP 420 | Provide targeted relief from residual charges for electric vehicle charging sites | The intent of this Change Proposal is to provide targeted relief from residual charges to publicly accessible electric vehicle (“EV”) charging sites. This may be a temporary fix to be put in place until the charging stations included are commercially viable. | General | 1 | Craig Booth / Richard Colwill | Thomas Holderness | 2023-03-29 | 19 | Yes - See comments in status column | TBC | The DCUSA Secretariat completed an initial draft of an impact assessment and presented this to the Working Group. The Working Group identified a number of actions required to make the analysis robust and fit for purpose. These actions are being progressed offline and the next meeting will be arrange via a poll. A NESO representative has offered to provide help in understanding the TNUoS impacts of this CP, however it has been challenging to identify a convenient time to meet to complete the work. This is being progress as a matter of priority. | #REF!
DCP 424 | Use of System charging for complex sites | This change proposal enables the correct DUoS to be paid by meters that are class F or G within a Class 5 or Class 6 Complex Site as described in BSC Modification P441 (where netting of Import and Export takes place for BSC Settlement purposes) in a practical manner. Under p441 where generation and demand are netted before settlement, the gross values must be added to the D0036 or D0275 to ensure the correct DUoS is charged. However, for class F and G the MPAN counts are included on the D0030 data flows but the volumes are zero. In order for the volumes to be correctly charged DUoS it is proposed that these volumes are included in the D0036 or D0275 using a pseudo MPAN for the gross value. | CDCM | 1 | Andy Green / Craig Booth | TBC | 2023-10-05 | 8 | No | Aligned to BSC Mod P441 Implementation Date | Bi lateral calls with REC, BSC and suppliers have taken place since the meeting on 11 December. Legal text is being updated and will be reviewed at the next Working Group in early Febuary.
DCP 442 | Aligning enduring flexible connections | The intent of this Change Proposal is to align (and clarify) the two approaches that currently may result in a flexible connection being provided on an enduring basis. A flexible connection on an enduring basis is an arrangement that allows a Customer’s import/export of electricity via a connection to be restricted by a DNO/IDNO Party in perpetuity. This CP proposes that such a connection shall be a Flexible Connection rather than a Curtailable Connection. | General | 1 | Melissa Kendal / Craig Booth | TBC | 2024-07-01 | 7 | Yes - See comments in status column | 2026-04-01 | The next Working Group is currently TBC - due to the Proposer's availability. Once the next meeting has been scheduled, the aim is to finalise the draft Consultation ready to issue to wider industry. | DEFINITION
DCP 443 | Excess Capacity | The purpose of this Change Proposal is to drive the correct customer behaviour regarding exceeding capacity. | CDCM / EDCM | 1 | Melissa Kendal / Andy Green | TBC | 2024-09-07 | 16 | No | 2026-01-04 | The publication of final tariffs has now been completed. A draft Consultation will be shared with the Working Group and a meeting poll will be issued via poll.
DCP 454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | The intent of this CP is to provide enduring targeted relief from residual charges to publicly accessible electric vehicle (“EV”) charging sites. | CDCM | 1 | Craig Booth / Richard Colwill | Thomas Holderness | 2025-05-06 | 1 | Yes - See comments in status column | 2028-04-01 | The DCUSA Secretariat completed an initial draft of an impact assessment and presented this to the DCP 420 Working Group. The same impact assessment will form the basis of the impact assessment for DCP 454, but will be amended. The DCP 420 update is therefore relevant to this. | #REF!
DCP 459 | DNO invoices to Embedded DNO | The intent of the Change Proposal is to require separate invoice backing data to be provided by DNO Parties when issuing invoices to EDNOs. | General | 3 | Hannah Proffitt / Andy Green | N/A | 2025-08-01 | 2 | No | 2026-02-26 | The Working Group met on 09 March to review the RFI responses and discuss next steps. The group are due to meet again on 20 March, with a representative from St Clements (DNO billing provider) to discuss the future of DNO/IDNO DUoS billing. The group will also discuss the legal text.
DCP 461 | Reducing the Impact of Transmission Distribution Charges | This Change Proposal seeks to address a growing set of structural, economic, and policy misalignments that are actively hindering the UK’s energy transition. | CCCM | 1 | Melissa Kendal / Craig Booth | N/A | 2025-08-13 | 14 | No | TBC | The Working Group met on 19 February 2026 to further develop the Consultation 2 document. The Secretariat is currently finalsing the draft Consultation document and legal text options for the Working Group to review prior to issuing to wider industry for further feedback. This review may be able to happen offline, however, a meeting will be scheduled if required. The next Working Group meeting is currently TBC.
DCP 463 | Charging non-consuming De-energised CT-Metered sites | This Change Proposal seeks to charge DUoS fixed and capacity charges to non-consuming CT-metered de-energised sites. | CCCM | 1 | Hannah Proffitt / Andy Green | N/A | 2025-09-05 | 6 | No | 2027-04-01 | The second consultation closed on 25 February. The Working Group met on 02 March to begin reviewing responses. The group agreed to meet again on 11 March to complete the review and to discuss next steps. |  | POST CONSULTATION 2 REFINEMENT
DCP 464 | IDNO Connection Applications: Treatment of Existing Assets | The intent of this Change Proposal is to clarify and align the DNO approach to the charging methodology applied to network asset(s) for IDNO applications when the IDNO is the sole user of specific network asset(s). | General | 1 | Melissa Kendal / Andy Green | N/A | 2025-09-08 | 6 | No | 2026-04-01 | The Working Group met on 17 February 2026 to continue to review the collated Consultation responses. The next Working Group meeting is scheduled for 12 March 2026 to review the legal text and develop the solution.
DCP 465 | NFD Generator and Battery Capacity Charges | The CDCM differs from the EDCM in that it does not treat generation sites differently to demand sites when determining the Capacity charge. This change proposal is to align The Differential In Generator and Battery Capacity charges between the two methodologies and therefore reduce the capacity charges for CDCM Generators and Batteries. | CDCM | 1 | Melissa Kendal / Craig Booth | TBC | 2025-10-15 | 2 | No | 2028-04-01 | The Working Group met on 03 March 2026 to review the collated RFI responses. The Working Group agreed that it would be beneficial to have DNO data from 2025/26 and 2027/28 as well as the 2026/27 data that was initially requested in the first RFI, andf therefore a second RFI for this data has been issued. The response deadline for this response is 17 March 2026. The next Working Group meeting is scheduled for 24 March 2026 to review the second RFI collated responses.
DCP 466 | Tariff Band to Follow Capacity | To ensure tariff bands for HH settled sites are aligned to a customer’s capacity at all times (e.g. tariff bands are assessed/changed whenever a capacity change is agreed.) | General | 1 | Melissa Kendal / Richard Colwill | TBC | 23/10.2025 | 5 | No | TBC | The Working Group met on 06 March 2026 to continue ro review the collated Consultation responses and agree next steps. The Working Group agreed to issue an RFI to wider industry. The next Working Group meeting is scheduled for 31 March 2026 where the collated RFI responses will be reviewed. |  | POST CONSULTATION REFINEMENT
DCP 467 | Online reporting tools for Category A and B defects | To mandate that relevant DCUSA Parties utilise online reporting tools where DNOs have made them available for the purpose of reporting Category A and B situations. | General | 2 | Hannah Proffitt / Richard Colwill | TBC | 2025-12-10 | 1 | No | TBC | The first Working Group meeting was held on 12 January 2026. Members discussed the proposal and agreed to issue an RFI to seek further information from parties. This is being drafted offline.
DCP 468 | Remove Redundant DataFlow from DTC/EMDS | D0164 / MM00069 might be a redundant relic from 1998. The Proposer can find no current obligation, nor any right, under DCUSA which would either be discharged or exercised (respectively) by its use. If no longer required, any such redundant data flows should be removed from DTC/EMDS. | General | 2 | Melissa Kendal / Craig Booth | N/A |  | 1 | No | 2026-11-05 | The first Working Group meeting was held on 26 February 2026. A draft Consultation has been circulated to the Working Group for review, with the aim to issue the Consultation to wider industry no later than 14 March 2026.
DCP 469 | Cross Code Standardisation of Charging Arrangement Notice Periods | Cross Code standardisation of Charging Arrangement Notice Periods. | General | 1 | Melissa Kendal / Richard Colwill |  |  | 1 | No | 2026-09-30 | The first Working Group was held on 11 February 2026 and a draft RFI has been produced. The Working Group will schedule a short meeting (TBC) for a final review of the RFI before it is issued to wider industry for further feedback.
DCP 470 | Independent Credit Assessments | The purpose of this Change Proposal is to allow the Company to apply an independent credit assessment where a User has not requested it. | General | 2 | Melissa Kendal / Andy Green |  |  | 1 | No | 2026-06-25 | The first Working Group was held on 12 February 2026. The Consultation was issued to wider industry on 20 February, with a response deadline of 13 March 2026. The next Working Group meeting is scheduled for 20 March 2026 to review the collated Consultation responses. |  | CONSULTATION
STATUS - CHANGE REPORT
DCP 452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | The intent of this Change Proposal is to correct an oversight in DCUSA which results in customers connecting directly to Grid Supply Point incorrectly facing a locational FCP charge relating to assets downstream of their connection. | EDCM | 1 | George Kestner / Dylan Townsend | Thomas Holderness | 2025-02-28 | 12 | No | 2028-04-01 | The Working Group issued a consultation on 16 December. The next Working Group held its final meeting on 02 March 2026, the complete a final review of the Change Report and Collated Consultation Responses. The Change Report is being issued to the March Panel for approval to be issued for voting. | DEFINITION | CHANGE REPORT
STATUS - VOTING
N/A | N/A | [7 empty] | No
STATUS - AWAITING AUTHORITY CONSENT
DCP 412 | Allocation of banding for TCR Charges for ‘Peaky’ Final Demand Customers | The intent of this CP is to consider the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Craig Booth / Richard Colwill | Andrew Malley | 2022-10-11 | 39 | No | 10 Working Days following Authority Decision | The Working Group have finalised the change report and legal text and this is being tabled at the February Panel. DCP 412 was approved by the Panel during their meeting in February and subsequently issued to Parties for voting on 20 February 2025, with a deadline of 13 March 2025. A Change Declaration was issued to both Parties and Ofgem on 19 March 2025. The Authority has seen been in touch to request the Secretariat conducts additional work on the impact assessment (this is not a send back). | AWAITING AUTHORITY CONSENT |  | 2025-03-19 | TBC
STATUS - AWAITING IMPLEMENTATION
2027-04-01
DCP 440 | Consuming “de-energised” sites | To ensure all consuming “de-energised” sites are charged DUoS. | CDCM | 1 | Hannah Proffitt / Andy Green | Shaun McRaith | 2024-03-14 | 10 | No | 2027-04-01 | On 29 August 2025, Ofgem issued their decision to approve DCP 456. DCP 440 will be implemented on 01/04/2027.
DCP 450 | Managing the effects of surplus residual charge in the CDCM | To determine the appropriate arrangements for managing the effects of large residual values in the CDCM. | CDCM | 1 | Hannah Proffitt / Craig Booth | James Harvey | 2025-02-10 | 3 | No | 2027-04-01 | On 20 October 2025, Ofgem published their decision to accept DCP 450. The Change is now awaiting implementation. DCP 450 will be implemented on 01/04/2027.
STATUS - SENT BACK
DCP 446 | Emergency Disconnections | To enable distributors to charge customers covered by section 2 of the National Terms of Connection for emergency disconnections that have been caused by their act or omission. | General | 1 | Hannah Proffitt / Craig Booth | N/A | 2024-11-07 | 3 | No | Next scheduled release following approval | A Change Declaration was issued to both Parties and Ofgem on 17 April 2025. Ofgem issued their decision to 'Send Back' DCP 446 for further assessment on 02 March 2026. The Secreatriat has informed Parties of the 'Send Back' and have contacted members of the Working Group in order to start the process of addressing the matters set out in Ofgem's decision letter. | AWAITING AUTHORITY CONSENT | SENT BACK | 2025-04-17
STATUS - IMPLEMENTED
DCP 455 | Align RAV price-inflation with that used in ED2 | ED2 PCFM uses a combination of RPI and CPIH to uplift from 2020/21 to outturn prices. This change seeks to align the prescribed calculation of RAV in Schedule 1, to retain consistency of credit cover calculation with ED2 PCFM. | General | 2 | Hannah Proffitt / Richard Colwill | N/A | 2025-05-22 | 0 | No | 2026-02-26 | DCP 455 was implemented on 26/02/2026 - this follows on from the Party voting, the outcome for which was a decision that the change be made. |  | IMPLEMENTED
STATUS - REJECTED
N/A
STATUS - WITHDRAWN
DCP 423 | LDNO Discounts for negative scaling | The purpose of this change proposal is to set a floor on the LDNO discount applied to negative tariff components, after scaling, for demand tariffs. The intent of this change proposal is to seek to remedy what the proposer believes is an unintended outcome of the implementation of Ofgem’s Targeted Charging Review where LDNO tariffs can be higher than the equivalent all-the-way tariff i.e. the LDNO margin is negative for that component. | CDCM | 1 | Melissa Kendal / Andy Green | TBC | 45055 | 7 | No | 2026-04-01 | The proposer advised that they wished to formally withdraw DCP 423 and this was communicated to Parties on 06 February 2026, by way of an email explaining that Parties had 10 Working Days to confirm if they wished to sponsor it moving forward. No Parties came forward to sponsor the change and it was subsequently Withdrawn. |  | WITHDRAWN
Change Register - March 2026

## Status Changes
[14 empty] | AWAITING IMPLEMENTATION | 0
[14 empty] | IMPLEMENTED | 0
[14 empty] | REJECTED | 0
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status | Status Changed in the last month | DEFINITION | 2
DCP 463 | Charging non-consuming De-energised CT-Metered sites | This Change Proposal seeks to charge DUoS fixed and capacity charges to non-consuming CT-metered de-energised sites. | CCCM | 1 | Hannah Proffitt / Andy Green | N/A | 2025-09-05 | 6 | No | 46478 | The second consultation closed on 25 February. The Working Group met on 02 March to begin reviewing responses. The group agreed to meet again on 11 March to complete the review and to discuss next steps. | 0 | POST CONSULTATION 2 REFINEMENT
DCP 466 | Tariff Band to Follow Capacity | To ensure tariff bands for HH settled sites are aligned to a customer’s capacity at all times (e.g. tariff bands are assessed/changed whenever a capacity change is agreed.) | General | 1 | Melissa Kendal / Richard Colwill | TBC | 23/10.2025 | 5 | No | TBC | The Working Group met on 06 March 2026 to continue ro review the collated Consultation responses and agree next steps. The Working Group agreed to issue an RFI to wider industry. The next Working Group meeting is scheduled for 31 March 2026 where the collated RFI responses will be reviewed. | 0 | POST CONSULTATION REFINEMENT
DCP 470 | Independent Credit Assessments | The purpose of this Change Proposal is to allow the Company to apply an independent credit assessment where a User has not requested it. | General | 2 | Melissa Kendal / Andy Green | 0 | 0 | 1 | No | 2026-06-25 | The first Working Group was held on 12 February 2026. The Consultation was issued to wider industry on 20 February, with a response deadline of 13 March 2026. The next Working Group meeting is scheduled for 20 March 2026 to review the collated Consultation responses. | 0 | CONSULTATION
DCP 452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | The intent of this Change Proposal is to correct an oversight in DCUSA which results in customers connecting directly to Grid Supply Point incorrectly facing a locational FCP charge relating to assets downstream of their connection. | EDCM | 1 | George Kestner / Dylan Townsend | Thomas Holderness | 2025-02-28 | 12 | No | 46844 | The Working Group issued a consultation on 16 December. The next Working Group held its final meeting on 02 March 2026, the complete a final review of the Change Report and Collated Consultation Responses. The Change Report is being issued to the March Panel for approval to be issued for voting. | DEFINITION | CHANGE REPORT
DCP 446 | Emergency Disconnections | To enable distributors to charge customers covered by section 2 of the National Terms of Connection for emergency disconnections that have been caused by their act or omission. | General | 1 | Hannah Proffitt / Craig Booth | N/A | 2024-11-07 | 3 | No | Next scheduled release following approval | A Change Declaration was issued to both Parties and Ofgem on 17 April 2025. Ofgem issued their decision to 'Send Back' DCP 446 for further assessment on 02 March 2026. The Secreatriat has informed Parties of the 'Send Back' and have contacted members of the Working Group in order to start the process of addressing the matters set out in Ofgem's decision letter. | AWAITING AUTHORITY CONSENT | SENT BACK
DCP 455 | Align RAV price-inflation with that used in ED2 | ED2 PCFM uses a combination of RPI and CPIH to uplift from 2020/21 to outturn prices. This change seeks to align the prescribed calculation of RAV in Schedule 1, to retain consistency of credit cover calculation with ED2 PCFM. | General | 2 | Hannah Proffitt / Richard Colwill | N/A | 2025-05-22 | 0 | No | 46079 | DCP 455 was implemented on 26/02/2026 - this follows on from the Party voting, the outcome for which was a decision that the change be made. | 0 | IMPLEMENTED
DCP 423 | LDNO Discounts for negative scaling | The purpose of this change proposal is to set a floor on the LDNO discount applied to negative tariff components, after scaling, for demand tariffs. The intent of this change proposal is to seek to remedy what the proposer believes is an unintended outcome of the implementation of Ofgem’s Targeted Charging Review where LDNO tariffs can be higher than the equivalent all-the-way tariff i.e. the LDNO margin is negative for that component. | CDCM | 1 | Melissa Kendal / Andy Green | TBC | 2023-05-09 | 7 | No | 46113 | The proposer advised that they wished to formally withdraw DCP 423 and this was communicated to Parties on 06 February 2026, by way of an email explaining that Parties had 10 Working Days to confirm if they wished to sponsor it moving forward. No Parties came forward to sponsor the change and it was subsequently Withdrawn. | 0 | WITHDRAWN
Status Change - March 2026

## Timetables
DCP | Title | Part 1/ Part 2 Matter | Timetable Change | Mar | Apr | May | Jun | Jul | Aug | Sep
470 | Independent Credit Assessments | Part 2 | N | Mar: CON; Apr: DEF; May: DEF; Jun: CR
469 | Cross Code Standardisation of Charging Arrangement Notice Periods | Part 1 | N | Mar: CON; Apr: DEF; May: DEF; Jun: CR
468 | Remove Redundant DataFlow from DTC/EMDS | Part 2 | N | Mar: CON; Apr: DEF; May: DEF; Jun: CR
467 | Online reporting tools for Category A and B defects | Part 1 | N | Mar: DEF; Apr: CR
466 | To ensure tariff bands for HH settled sites are aligned to a customer’s capacity at all times (e.g. tariff bands are assessed/changed whenever a capacity change is agreed.) | Part 1 | N | Mar: DEF; Apr: CR
465 | NFD Generator and Battery Capacity Charges | Part 1 | N | CON | DEF | DEF | DEF | DEF | DEF | CR
464 | IDNO Connection Applications: Treatment of Existing Assets | Part 1 | bar: N N to DEF CON
Timetable Change |  |  | DEF CON: DEF; CR DEF: DEF; CR DEF: CR
463 | Charging non-consuming De-energised CT-Metered sites | Part 1 | bar: N N to DEF CON
Timetable Change |  |  | DEF CON: DEF; CR DEF: DEF; CR DEF: CR
461 | Reducing the Impact of Transmission Distribution Charges | Part 1 | N N: N; DEF CON: DEF; CR DEF: CR
459 | DNO invoices to Embedded DNO | Part 1 | N N: N; DEF CON: DEF; CR DEF: CR
454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | Part 1 | N | DEF | CON | DEF | DEF | CR
452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | Part 1 | bar: N N to DEF CON
443 | Excess Capacity | Part 1 | bar: N N to DEF CON
Timetable Change |  |  | DEF CON: DEF; CR DEF: DEF; CR DEF: CR
442 | Aligning enduring flexible connections | Part 1 | N N: N; DEF CON: O/H
424 | Use of System charging for complex sites | Part 1 | N | DEF | DEF | DEF | CR
420 | Include Car Charging Stations In The Definition For Non Final Demand | Part 1 | N N: N; DEF CON: DEF; CR DEF: CON; CR DEF: CR
419 | Pre-notification of Planned Supply De-energisations | Part 1 | N N: N; DEF CON: O/H
388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | Part 1 | N N: N; DEF CON: O/H
| DEFINITION | DEF
| RFI | RFI
| CONSULTATION | CON/ CON 2
| CHANGE REPORT | CR
| ON HOLD | O/H

## Legal Text Overlap Tracker
YES
|  | DCP 424 | DCP 388 | DCP 412 | DCP 420 | DCP 440 | DCP 450 | DCP 443 | DCP 463 | DCP 452
|  | 2026-12-31 | 2027-01-18 | TBC | 2026-11-01 | 2027-04-01 | 2027-04-01 | 2026-04-01 | 2027-04-01 | 2028-04-01 |  | NOTES TO ASSIST
Schedules | Paragraph Number | Definition | On Hold | Awaiting Consent | Definition | Awaiting Implementation | Awaiting Implementation | Definition | Definition | Change Report | Number of CPs Impacting Paragraph
Schedule 15 | - | [9 empty] | 0
0
Schedule 16 | Introduction | [9 empty] | 0
Schedule 16 | 1 | [9 empty] | 0
Schedule 16 | 2 | [9 empty] | 0
Schedule 16 | 3 | [9 empty] | 0
Schedule 16 | 4 | [9 empty] | 0
Schedule 16 | 5 | [9 empty] | 0
Schedule 16 | 6 | [9 empty] | 0
Schedule 16 | 7 | [9 empty] | 0
Schedule 16 | 7A | [9 empty] | 0
Schedule 16 | 8 | [9 empty] | 0
Schedule 16 | 9 | [9 empty] | 0
Schedule 16 | 10 | [9 empty] | 0
Schedule 16 | 10A | [9 empty] | 0
Schedule 16 | 11 | [9 empty] | 0
Schedule 16 | 12 | [9 empty] | 0
Schedule 16 | 13 | [9 empty] | 0
Schedule 16 | 14 | [9 empty] | 0
Schedule 16 | 15 | [9 empty] | 0
Schedule 16 | 16 | [9 empty] | 0
Schedule 16 | 17 | [9 empty] | 0
Schedule 16 | 18 | [9 empty] | 0
Schedule 16 | 19 | [9 empty] | 0
Schedule 16 | 20 | [9 empty] | 0
Schedule 16 | 21 | [9 empty] | 0
Schedule 16 | 22 | [9 empty] | 0
Schedule 16 | 23 | [9 empty] | 0
Schedule 16 | 24 | [9 empty] | 0
Schedule 16 | 25 | [9 empty] | 0
Schedule 16 | 26 | [9 empty] | 0
Schedule 16 | 27 | [9 empty] | 0
Schedule 16 | 28 | [9 empty] | 0
Schedule 16 | 29 | [9 empty] | 0
Schedule 16 | 30 | [9 empty] | 0
Schedule 16 | 31 | [9 empty] | 0
Schedule 16 | 32 | [9 empty] | 0
Schedule 16 | 33 | [9 empty] | 0
Schedule 16 | 34 | [9 empty] | 0
Schedule 16 | 35 | [9 empty] | 0
Schedule 16 | 36 | [9 empty] | 0
Schedule 16 | 37 | [9 empty] | 0
Schedule 16 | 38 | [9 empty] | 0
Schedule 16 | 39 | [9 empty] | 0
Schedule 16 | 40 | [9 empty] | 0
Schedule 16 | 41 | [9 empty] | 0
Schedule 16 | 41A | [9 empty] | 0
Schedule 16 | 41B | [9 empty] | 0
Schedule 16 | 42 | [9 empty] | 0
Schedule 16 | 42A | [9 empty] | 0
Schedule 16 | 43 | [9 empty] | 0
Schedule 16 | 44 | [9 empty] | 0
Schedule 16 | 45 | [9 empty] | 0
Schedule 16 | 46 | [9 empty] | 0
Schedule 16 | 47 | [9 empty] | 0
Schedule 16 | 48 | [9 empty] | 0
Schedule 16 | 49 | [9 empty] | 0
Schedule 16 | 50 | [9 empty] | 0
Schedule 16 | 51 | [9 empty] | 0
Schedule 16 | 52 | [9 empty] | 0
Schedule 16 | 52A | [9 empty] | 0
Schedule 16 | 53 | [9 empty] | 0
Schedule 16 | 54 | [9 empty] | 0
Schedule 16 | 55 | [9 empty] | 0
Schedule 16 | 56 | [9 empty] | 0
Schedule 16 | 57 | [9 empty] | 0
Schedule 16 | 58 | [9 empty] | 0
Schedule 16 | 59 | [9 empty] | 0
Schedule 16 | 60 | [9 empty] | 0
Schedule 16 | 61 | [9 empty] | 0
Schedule 16 | 62 | [9 empty] | 0
Schedule 16 | 63 | [9 empty] | 0
Schedule 16 | 64 | [9 empty] | 0
Schedule 16 | 65 | [9 empty] | 0
Schedule 16 | 66 | [9 empty] | 0
Schedule 16 | 67 | [9 empty] | 0
Schedule 16 | 68 | [9 empty] | 0
Schedule 16 | 69 | [9 empty] | 0
Schedule 16 | 70 | [9 empty] | 0
Schedule 16 | 71 | [9 empty] | 0
Schedule 16 | 72 | [9 empty] | 0
Schedule 16 | 72A | [9 empty] | 0
Schedule 16 | 73 | [9 empty] | 0
Schedule 16 | 74 | [9 empty] | 0
Schedule 16 | 75 | [9 empty] | 0
Schedule 16 | 76 | [9 empty] | 0
Schedule 16 | 77 | [9 empty] | 0
Schedule 16 | 78 | [9 empty] | 0
Schedule 16 | 79 | [9 empty] | 0
Schedule 16 | 80 | [9 empty] | 0
Schedule 16 | 81 | [9 empty] | 0
Schedule 16 | 82 | [9 empty] | 0
Schedule 16 | 83 | [9 empty] | 0
Schedule 16 | 84 | [9 empty] | 0
Schedule 16 | 85 | [9 empty] | 0
Schedule 16 | 86 | [9 empty] | 0
Schedule 16 | 87 | [9 empty] | 0
Schedule 16 | 88 | [9 empty] | 0
Schedule 16 | 89 | [9 empty] | 0
Schedule 16 | 90 | [9 empty] | 0
Schedule 16 | 91 | [9 empty] | 0
Schedule 16 | 92 | [9 empty] | 0
Schedule 16 | 92A | [9 empty] | 0
Schedule 16 | 92B | [9 empty] | 0
Schedule 16 | 92C | [9 empty] | 0
Schedule 16 | 93 | [9 empty] | 0
Schedule 16 | 94 | [9 empty] | 0
Schedule 16 | 94A | [9 empty] | 0
Schedule 16 | 94B | [5 empty] | YES |  |  |  | 1
Schedule 16 | 95 | [9 empty] | 0
Schedule 16 | 96 | [9 empty] | 0
Schedule 16 | 97 | [9 empty] | 0
Schedule 16 | 98 | [9 empty] | 0
Schedule 16 | 99 | [9 empty] | 0
Schedule 16 | 100 | [9 empty] | 0
Schedule 16 | 101 | [9 empty] | 0
Schedule 16 | 102 | [9 empty] | 0
Schedule 16 | 102A | [9 empty] | 0
Schedule 16 | 102B | [9 empty] | 0
Schedule 16 | 103 | [9 empty] | 0
Schedule 16 | 104 | [9 empty] | 0
Schedule 16 | 105 | [9 empty] | 0
Schedule 16 | 106 | [9 empty] | 0
Schedule 16 | 107 | [9 empty] | 0
Schedule 16 | 108 | [9 empty] | 0
Schedule 16 | 108A | [9 empty] | 0
Schedule 16 | 109 | [9 empty] | 0
Schedule 16 | 110 | [9 empty] | 0
Schedule 16 | 111 | [9 empty] | 0
Schedule 16 | 112 | [9 empty] | 0
Schedule 16 | 112A | [9 empty] | 0
Schedule 16 | 113 | [9 empty] | 0
Schedule 16 | 113A | [9 empty] | 0
Schedule 16 | 113B | [9 empty] | 0
Schedule 16 | 113C | [9 empty] | 0
Schedule 16 | 113D | [9 empty] | 0
Schedule 16 | 113E | [9 empty] | 0
Schedule 16 | 114 | [9 empty] | 0
Schedule 16 | 115 | [9 empty] | 0
Schedule 16 | 116 | [9 empty] | 0
Schedule 16 | 117 | [9 empty] | 0
Schedule 16 | 118 | [9 empty] | 0
Schedule 16 | 119 | [9 empty] | 0
Schedule 16 | 120 | [9 empty] | 0
Schedule 16 | 121 | [9 empty] | 0
Schedule 16 | 122 | [9 empty] | 0
Schedule 16 | 123 | [9 empty] | 0
Schedule 16 | 124 | [9 empty] | 0
Schedule 16 | 125 | [9 empty] | 0
Schedule 16 | 126 | [9 empty] | 0
Schedule 16 | 127 | [9 empty] | 0
Schedule 16 | 127A | [9 empty] | 0
Schedule 16 | 128 | YES | [8 empty] | 1
Schedule 16 | 129 | [9 empty] | 0
Schedule 16 | 130 | [9 empty] | 0
Schedule 16 | 131 | [9 empty] | 0
Schedule 16 | 132 | [9 empty] | 0
Schedule 16 | 132A | [9 empty] | 0
Schedule 16 | 132B | [9 empty] | 0
Schedule 16 | 132C | [9 empty] | 0
Schedule 16 | 132D | [9 empty] | 0
Schedule 16 | 133 | [9 empty] | 0
Schedule 16 | 134 | [9 empty] | 0
Schedule 16 | 135 | [9 empty] | 0
Schedule 16 | 135A | [9 empty] | 0 | MHHS CP seeks to remove the last column containing applicable Measurement Class
Schedule 16 | 135B | [9 empty] | 0
Schedule 16 | 136 | [9 empty] | 0
Schedule 16 | 137 | [9 empty] | 0
Schedule 16 | 138 | [9 empty] | 0
Schedule 16 | 139 |  |  |  |  | YES |  |  | YES |  | 2
Schedule 16 | 140 |  |  |  |  | YES |  |  | YES |  | 2
Schedule 16 | 140A | [9 empty] | 0
Schedule 16 | 140B | [9 empty] | 0
Schedule 16 | 140C | [9 empty] | 0
Schedule 16 | 140D | [9 empty] | 0
Schedule 16 | 140E | [9 empty] | 0
Schedule 16 | 141 | [9 empty] | 0
Schedule 16 | 142 | [9 empty] | 0
Schedule 16 | 143 | [9 empty] | 0
Schedule 16 | 144 | [9 empty] | 0
Schedule 16 | 145 | [9 empty] | 0
Schedule 16 | 146 | [9 empty] | 0
Schedule 16 | 147 | [9 empty] | 0
Schedule 16 | 148 | [9 empty] | 0
Schedule 16 | 149 | [9 empty] | 0
Schedule 16 | 150 | [9 empty] | 0
Schedule 16 | 151 | [9 empty] | 0
Schedule 16 | 152 | [9 empty] | 0
Schedule 16 | 153 | [6 empty] | YES |  |  | 1
Schedule 16 | 154 | [9 empty] | 0
Schedule 16 | 155 | [9 empty] | 0
Schedule 16 | 156 | [9 empty] | 0
Schedule 16 | 157 | [9 empty] | 0
Schedule 16 | 158 | [9 empty] | 0
Schedule 16 | 159 | [9 empty] | 0
Schedule 16 | 160 | [9 empty] | 0
Schedule 16 | 161 | [9 empty] | 0
Schedule 16 | 162 | [9 empty] | 0
Schedule 16 | 163 | [9 empty] | 0
Schedule 16 | 164 | [9 empty] | 0
Schedule 16 | 165 | [9 empty] | 0
Schedule 16 | 166 | [9 empty] | 0
Schedule 16 | 167 | [9 empty] | 0
Schedule 16 | 168 | [9 empty] | 0
Schedule 16 | 169 | [9 empty] | 0
Schedule 16 | 170 | [9 empty] | 0
Schedule 16 | 171 | [9 empty] | 0
Schedule 16 | 172 | [9 empty] | 0
Schedule 16 | 173 | [9 empty] | 0
Schedule 16 | 173A | [9 empty] | 0 | DCP 439 Introduces new Paragraph 173A
Schedule 16 | 174 | [9 empty] | 0
Schedule 16 | 175 | [9 empty] | 0
Schedule 16 | 176 | [9 empty] | 0
Schedule 16 | 177 | [9 empty] | 0
Schedule 16 | 178 | [9 empty] | 0
Schedule 16 | 179 | [9 empty] | 0
Schedule 16 | 180 | [9 empty] | 0
Schedule 16 | 181 | [9 empty] | 0
Schedule 16 | 182 | [9 empty] | 0
Schedule 16 | 183 | [9 empty] | 0
Schedule 16 | 184 | [9 empty] | 0
Schedule 16 | Glossary | [9 empty] | 0
0
Schedule 17 | Introduction | [9 empty] | 0
Schedule 17 | 1 | [9 empty] | 0
Schedule 17 | 1.1 | [9 empty] | 0
Schedule 17 | 1.2 | [9 empty] | 0
Schedule 17 | 1.3 | [9 empty] | 0 | Model reference number and date
Schedule 17 | 1.3A | [9 empty] | 0
Schedule 17 | 1.4 | [9 empty] | 0
Schedule 17 | 1.5 | [9 empty] | 0
Schedule 17 | 1.6 | [9 empty] | 0
Schedule 17 | 1.7 | [9 empty] | 0
Schedule 17 | 1.8 | [9 empty] | 0
Schedule 17 | 1.9 | [9 empty] | 0
Schedule 17 | 2 | [9 empty] | 0
Schedule 17 | 2.1 | [9 empty] | 0
Schedule 17 | 2.2 | [9 empty] | 0
Schedule 17 | 2.3 | [9 empty] | 0
Schedule 17 | 2.4 | [9 empty] | 0
Schedule 17 | 2.5 | [9 empty] | 0
Schedule 17 | 2.6 | [9 empty] | 0
Schedule 17 | 2.7 | [8 empty] | YES | 1
Schedule 17 | 2.8 | [9 empty] | 0
Schedule 17 | 2.9 | [9 empty] | 0
Schedule 17 | 2.1 | [9 empty] | 0
Schedule 17 | 2.11 | [9 empty] | 0
Schedule 17 | 2.12 | [9 empty] | 0
Schedule 17 | 2.13 | [9 empty] | 0
Schedule 17 | 2.14 | [9 empty] | 0
Schedule 17 | 2.15 | [9 empty] | 0
Schedule 17 | 2.16 | [9 empty] | 0
Schedule 17 | 2.17 | [9 empty] | 0
Schedule 17 | 2.18 | [9 empty] | 0
Schedule 17 | 2.19 | [9 empty] | 0
Schedule 17 | 3 | [9 empty] | 0
Schedule 17 | 3.1 | [9 empty] | 0
Schedule 17 | 3.2 | [9 empty] | 0
Schedule 17 | 3.3 | [9 empty] | 0
Schedule 17 | 3.4 | [9 empty] | 0
Schedule 17 | 3.5 | [9 empty] | 0
Schedule 17 | 3.6 | [9 empty] | 0
Schedule 17 | 3.7 | [9 empty] | 0
Schedule 17 | 4 | [9 empty] | 0
Schedule 17 | 4.1 | [9 empty] | 0
Schedule 17 | 5 | [9 empty] | 0
Schedule 17 | 5.1 | [9 empty] | 0
Schedule 17 | 6 | [9 empty] | 0
Schedule 17 | 6.1 | [9 empty] | 0
Schedule 17 | 6.2 | [8 empty] | YES | 1
Schedule 17 | 6.3 | [8 empty] | YES | 1
Schedule 17 | 7 | [9 empty] | 0
Schedule 17 | 7.1 | [9 empty] | 0
Schedule 17 | 8 | [9 empty] | 0
Schedule 17 | 8.1 | [9 empty] | 0
Schedule 17 | 8.2 | [9 empty] | 0
Schedule 17 | 8.3 | [9 empty] | 0
Schedule 17 | 8.4 | [9 empty] | 0
Schedule 17 | 9 | [9 empty] | 0
Schedule 17 | 9.1 | [9 empty] | 0
Schedule 17 | 9.2 | [9 empty] | 0
Schedule 17 | 9.3 | [9 empty] | 0
Schedule 17 | 10 | [9 empty] | 0
Schedule 17 | 10.1 | [9 empty] | 0
Schedule 17 | 10.2 | [9 empty] | 0
Schedule 17 | 10.3 | [9 empty] | 0
Schedule 17 | 10.4 | [9 empty] | 0
Schedule 17 | 11 | [9 empty] | 0
Schedule 17 | 11.1 | [9 empty] | 0
Schedule 17 | 12 | [9 empty] | 0
Schedule 17 | 12.1 | [9 empty] | 0
Schedule 17 | 12.2 | [9 empty] | 0
Schedule 17 | 12.3 | [9 empty] | 0
Schedule 17 | 13 | [9 empty] | 0
Schedule 17 | 13.1 | [9 empty] | 0
Schedule 17 | 13.2 | [9 empty] | 0
Schedule 17 | 13.3 | [9 empty] | 0
Schedule 17 | 13.4 | [9 empty] | 0
Schedule 17 | 14 | [9 empty] | 0
Schedule 17 | 14.1 | [9 empty] | 0
Schedule 17 | 14.2 | [9 empty] | 0
Schedule 17 | 14.3 | [9 empty] | 0
Schedule 17 | 14.4 | [9 empty] | 0
Schedule 17 | 14.5 | [9 empty] | 0
Schedule 17 | 15 | [9 empty] | 0
Schedule 17 | 15.1 | [9 empty] | 0
Schedule 17 | 15.2 | [9 empty] | 0
Schedule 17 | 15.3 | [9 empty] | 0
Schedule 17 | 15.4 | [9 empty] | 0
Schedule 17 | 15.5 | [9 empty] | 0
Schedule 17 | 15.6 | [9 empty] | 0
Schedule 17 | 15.7 | [9 empty] | 0
Schedule 17 | 15.8 | [9 empty] | 0
Schedule 17 | 15.9 | [9 empty] | 0
Schedule 17 | 15.1 | [9 empty] | 0
Schedule 17 | 15.11 | [9 empty] | 0
Schedule 17 | 15.12 | [9 empty] | 0
Schedule 17 | 15.15 | [9 empty] | 0
Schedule 17 | 16 | [9 empty] | 0
Schedule 17 | 16.1 | [9 empty] | 0
Schedule 17 | 16.2 | [9 empty] | 0
Schedule 17 | 16.3 | [9 empty] | 0
Schedule 17 | 16.4 | [9 empty] | 0
Schedule 17 | 16.5 | [9 empty] | 0
Schedule 17 | 16.6 | [9 empty] | 0
Schedule 17 | 16.7 | [9 empty] | 0
Schedule 17 | 16.8 | [9 empty] | 0
Schedule 17 | 16.9 | [9 empty] | 0
Schedule 17 | 16.1 | [9 empty] | 0
Schedule 17 | 17 | [9 empty] | 0
Schedule 17 | 17.1 | [9 empty] | 0
Schedule 17 | 17.2 | [9 empty] | 0
Schedule 17 | 17.3 | [9 empty] | 0
Schedule 17 | 18 | [9 empty] | 0
Schedule 17 | 18.1 | [9 empty] | 0
Schedule 17 | 18.2 | [9 empty] | 0
Schedule 17 | 18.3 | [9 empty] | 0
Schedule 17 | 18.4 | [9 empty] | 0
Schedule 17 | 18.5 | [9 empty] | 0
Schedule 17 | 18.6 | [9 empty] | 0
Schedule 17 | 18.7 | [9 empty] | 0
Schedule 17 | 18.8 | [9 empty] | 0
Schedule 17 | 18.9 | [9 empty] | 0
Schedule 17 | 18.1 | [9 empty] | 0
Schedule 17 | 18.11 | [9 empty] | 0
Schedule 17 | 18.12 | [9 empty] | 0
Schedule 17 | 18.13 | [9 empty] | 0
Schedule 17 | 18.14 | [9 empty] | 0
Schedule 17 | 18.15 | [9 empty] | 0
Schedule 17 | 18.16 | [9 empty] | 0
Schedule 17 | 18.17 | [9 empty] | 0
Schedule 17 | 18.18 | [9 empty] | 0
Schedule 17 | 18.19 | [9 empty] | 0
Schedule 17 | 18.2 | [9 empty] | 0
Schedule 17 | 18.21 | [9 empty] | 0
Schedule 17 | 19 | [9 empty] | 0
Schedule 17 | 19.1 | [9 empty] | 0
Schedule 17 | 19.2 | [9 empty] | 0
Schedule 17 | 19.3 | [9 empty] | 0
Schedule 17 | 19.4 | [9 empty] | 0
Schedule 17 | 19.5 | [9 empty] | 0
Schedule 17 | 19.6 | [9 empty] | 0
Schedule 17 | 19.7 | [9 empty] | 0
Schedule 17 | 19.8 | [9 empty] | 0
Schedule 17 | 19.9 | [9 empty] | 0
Schedule 17 | 19.1 | [9 empty] | 0
Schedule 17 | 19.11 | [9 empty] | 0
Schedule 17 | 20 | [9 empty] | 0
Schedule 17 | 20.1 | [9 empty] | 0
Schedule 17 | 20.2 | [9 empty] | 0
Schedule 17 | 20.3 | [9 empty] | 0
Schedule 17 | 20.4 | [9 empty] | 0
Schedule 17 | 20.5 | [9 empty] | 0
Schedule 17 | 20.6 | [6 empty] | YES |  |  | 1
Schedule 17 | 20.7 | [6 empty] | YES |  |  | 1
Schedule 17 | 20.8 | [9 empty] | 0
Schedule 17 | 20.9 | [6 empty] | YES |  |  | 1
Schedule 17 | 21 | [9 empty] | 0
Schedule 17 | 21.1 | [9 empty] | 0
Schedule 17 | 21.2 | [9 empty] | 0
Schedule 17 | 22 | [9 empty] | 0
Schedule 17 | 22.1 | [9 empty] | 0
Schedule 17 | 22.2 | [9 empty] | 0
Schedule 17 | 22.3 | [9 empty] | 0
Schedule 17 | 22.4 | [9 empty] | 0
Schedule 17 | 23 | [9 empty] | 0
Schedule 17 | 23.1 | [9 empty] | 0
Schedule 17 | 23.2 | [9 empty] | 0
Schedule 17 | 23.3 | [9 empty] | 0
Schedule 17 | 23.4 | [9 empty] | 0
Schedule 17 | 23.5 | [9 empty] | 0
Schedule 17 | 24 | [9 empty] | 0
Schedule 17 | 24.1 | [9 empty] | 0
Schedule 17 | 24.2 | [9 empty] | 0
Schedule 17 | 24.3 | [9 empty] | 0
Schedule 17 | 24.4 | [9 empty] | 0
Schedule 17 | 24.5 | [9 empty] | 0
Schedule 17 | 24.6 | [9 empty] | 0
Schedule 17 | 24.7 | [9 empty] | 0
Schedule 17 | 24.8 | [9 empty] | 0
Schedule 17 | 24.9 | [9 empty] | 0
Schedule 17 | 25 | [9 empty] | 0
Schedule 17 | 25.1 | [9 empty] | 0
Schedule 17 | 25.2 | [9 empty] | 0
Schedule 17 | 25.3 | [9 empty] | 0
Schedule 17 | 25.4 | [9 empty] | 0
Schedule 17 | 25.5 | [9 empty] | 0
Schedule 17 | 25.6 | [9 empty] | 0
Schedule 17 | 25.7 | [9 empty] | 0
Schedule 17 | 25.8 | [9 empty] | 0
Schedule 17 | 25.9 | [9 empty] | 0
Schedule 17 | 25.1 | [9 empty] | 0
Schedule 17 | 25.11 | [9 empty] | 0
Schedule 17 | 25.12 | [9 empty] | 0
Schedule 17 | 25.13 | [9 empty] | 0
Schedule 17 | 25.14 | [9 empty] | 0
Schedule 17 | 25.15 | [9 empty] | 0
Schedule 17 | 25.16 | [9 empty] | 0
Schedule 17 | 25.17 | [9 empty] | 0
Schedule 17 | 25.18 | [9 empty] | 0
Schedule 17 | 25.19 | [9 empty] | 0
Schedule 17 | 26 | [9 empty] | 0
Schedule 17 | 26.1 | [9 empty] | 0
Schedule 17 | 26.2 | [9 empty] | 0
Schedule 17 | 26.3 | [9 empty] | 0
Schedule 17 | 26.4 | [9 empty] | 0
Schedule 17 | 26.5 | [9 empty] | 0
Schedule 17 | 26.6 | [9 empty] | 0
Schedule 17 | 26.7 | [9 empty] | 0
Schedule 17 | 26.8 | [9 empty] | 0
Schedule 17 | 26.9 | [9 empty] | 0
Schedule 17 | 26.1 | [9 empty] | 0
Schedule 17 | 26.11 | [9 empty] | 0
Schedule 17 | 27 | [9 empty] | 0
Schedule 17 | 27.1 | [9 empty] | 0
Schedule 17 | 27.2 | [9 empty] | 0
Schedule 17 | 27.3 | [9 empty] | 0
Schedule 17 | 27.4 | [9 empty] | 0
Schedule 17 | 28 | [9 empty] | 0
Schedule 17 | 28.1 | [9 empty] | 0
Schedule 17 | 28.2 | [9 empty] | 0
Schedule 17 | 29 | [9 empty] | 0
Schedule 17 | 29.1 | [9 empty] | 0
Schedule 17 | 29.2 | [9 empty] | 0
Schedule 17 | 29.3 | [9 empty] | 0
Schedule 17 | 29.4 | [9 empty] | 0
Schedule 17 | 30 | [9 empty] | 0
Schedule 17 | 30.1 | [9 empty] | 0
Schedule 17 | 30.2 | [9 empty] | 0
Schedule 17 | 30.3 | [9 empty] | 0
Schedule 17 | 30.4 | [9 empty] | 0
Schedule 17 | 30.5 | [9 empty] | 0
Schedule 17 | 30.6 | [9 empty] | 0
Schedule 17 | 30.7 | [9 empty] | 0
Schedule 17 | 30.8 | [9 empty] | 0
Schedule 17 | 30.9 | [9 empty] | 0
Schedule 17 | 30.1 | [9 empty] | 0
Schedule 17 | 30.11 | [9 empty] | 0
Schedule 17 | 31 | [9 empty] | 0 | DCP 439 Introduces new Paragraph 31
Schedule 17 | 31.1 | [9 empty] | 0 | DCP 439 Introduces new Paragraph 31.1
Schedule 17: Annex 1 | 1 | [9 empty] | 0
Schedule 17: Annex 1 | 2 | [9 empty] | 0
Schedule 17: Annex 1 | 2.1 | [9 empty] | 0
Schedule 17: Annex 1 | 2.2 | [9 empty] | 0
Schedule 17: Annex 1 | 2.3 | [9 empty] | 0
Schedule 17: Annex 1 | 2.4 | [9 empty] | 0
Schedule 17: Annex 1 | 2.5 | [9 empty] | 0
Schedule 17: Annex 1 | 3 | [9 empty] | 0
Schedule 17: Annex 1 | Definitions | [9 empty] | 0
Schedule 17: Annex 1 | 4 | [9 empty] | 0
Schedule 17: Annex 1 | 4.1 | [9 empty] | 0
Schedule 17: Annex 1 | 4.2 | [9 empty] | 0
Schedule 17: Annex 1 | 4.3 | [9 empty] | 0
Schedule 17: Annex 1 | 4.4 | [9 empty] | 0
Schedule 17: Annex 1 | 4.5 | [9 empty] | 0
Schedule 17: Annex 1 | 4.6 | [9 empty] | 0
Schedule 17: Annex 1 | 4.7 | [9 empty] | 0
Schedule 17: Annex 1 | 4.8 | [9 empty] | 0
Schedule 17: Annex 1 | 4.9 | [9 empty] | 0
Schedule 17: Annex 1 | 4.1 | [9 empty] | 0
Schedule 17: Annex 1 | 5 | [9 empty] | 0
Schedule 17: Annex 1 | 5.1 | [9 empty] | 0
Schedule 17: Annex 1 | 5.2 | [9 empty] | 0
Schedule 17: Annex 1 | 5.3 | [9 empty] | 0
Schedule 17: Annex 1 | 5.4 | [9 empty] | 0
Schedule 17: Annex 1 | 5.5 | [9 empty] | 0
Schedule 17: Annex 1 | 5.6 | [9 empty] | 0
Schedule 17: Annex 1 | 5.7 | [9 empty] | 0
Schedule 17: Annex 1 | 5.8 | [9 empty] | 0
Schedule 17: Annex 1 | 5.9 | [9 empty] | 0
Schedule 17: Annex 1 | 5.1 | [9 empty] | 0
Schedule 17: Annex 1 | 5.11 | [9 empty] | 0
Schedule 17: Annex 1 | 5.12 | [9 empty] | 0
Schedule 17: Annex 1 | 5.13 | [9 empty] | 0
Schedule 17: Annex 1 | 5.14 | [9 empty] | 0
Schedule 17: Annex 1 | 5.15 | [9 empty] | 0
Schedule 17: Annex 1 | 5.16 | [9 empty] | 0
Schedule 17: Annex 1 | 5.17 | [9 empty] | 0
Schedule 17: Annex 1 | 5.18 | [9 empty] | 0
Schedule 17: Annex 1 | 5.19 | [9 empty] | 0
Schedule 17: Annex 1 | 5.2 | [9 empty] | 0
Schedule 17: Annex 1 | 5.21 | [9 empty] | 0
Schedule 17: Annex 1 | 5.22 | [9 empty] | 0
Schedule 17: Annex 1 | 5.23 | [9 empty] | 0
Schedule 17: Annex 1 | 5.24 | [9 empty] | 0
Schedule 17: Annex 1 | 5.25 | [9 empty] | 0
Schedule 17: Annex 1 | 5.26 | [9 empty] | 0
Schedule 17: Annex 1 | 5.27 | [9 empty] | 0
Schedule 17: Annex 1 | 5.28 | [9 empty] | 0
Schedule 17: Annex 1 | 5.29 | [9 empty] | 0
Schedule 17: Annex 1 | 5.3 | [9 empty] | 0
Schedule 17: Annex 1 | 5.31 | [9 empty] | 0
Schedule 17: Annex 1 | 5.32 | [9 empty] | 0
Schedule 17: Annex 1 | 5.33 | [9 empty] | 0
Schedule 17: Annex 1 | 5.34 | [9 empty] | 0
Schedule 17: Annex 1 | 5.35 | [9 empty] | 0
Schedule 17: Annex 1 | 5.36 | [9 empty] | 0
Schedule 17: Annex 1 | 5.37 | [9 empty] | 0
Schedule 17: Annex 1 | 5.38 | [9 empty] | 0
Schedule 17: Annex 1 | 5.39 | [9 empty] | 0
Schedule 17: Annex 1 | 5.4 | [9 empty] | 0
Schedule 17: Annex 1 | 5.41 | [9 empty] | 0
Schedule 17: Annex 1 | 5.42 | [9 empty] | 0
Schedule 17: Annex 1 | 5.43 | [9 empty] | 0
Schedule 17: Annex 1 | 5.44 | [9 empty] | 0
Schedule 17: Annex 1 | 5.45 | [9 empty] | 0
Schedule 17: Annex 1 | 6 | [9 empty] | 0
Schedule 17: Annex 1 | 6.1 | [9 empty] | 0
Schedule 17: Annex 1 | 6.2 | [9 empty] | 0
Schedule 17: Annex 1 | 6.3 | [8 empty] | YES | 1
Schedule 17: Annex 1 | 6.4 | [9 empty] | 0
Schedule 17: Annex 1 | 6.5 | [9 empty] | 0
Schedule 17: Annex 1 | 6.6 | [9 empty] | 0
Schedule 17: Annex 1 | 6.7 | [9 empty] | 0
Schedule 17: Annex 1 | 6.8 | [9 empty] | 0
Schedule 17: Annex 1 | 7 | [9 empty] | 0
Schedule 17: Annex 1 | 7.1 | [9 empty] | 0
Schedule 17: Annex 1 | 7.2 | [9 empty] | 0
Schedule 17: Annex 1 | 7.3 | [9 empty] | 0
Schedule 17: Annex 1 | 7.4 | [9 empty] | 0
Schedule 17: Annex 1 | 7.5 | [9 empty] | 0
Schedule 17: Annex 1 | 7.6 | [9 empty] | 0
Schedule 17: Annex 1 | 7.7 | [9 empty] | 0
Schedule 17: Annex 1 | 7.8 | [9 empty] | 0
Schedule 17: Annex 1 | 8 | [9 empty] | 0
Schedule 17: Annex 1 | 8.1 | [9 empty] | 0
Schedule 17: Annex 1 | 8.2 | [9 empty] | 0
Schedule 17: Annex 1 | 8.3 | [9 empty] | 0
Schedule 17: Annex 1 | 8.4 | [9 empty] | 0
Schedule 17: Annex 1 | 9 | [9 empty] | 0
Schedule 17: Annex 1 | 9.1 | [9 empty] | 0
Schedule 17: Annex 1 | 9.2 | [9 empty] | 0
Schedule 17: Annex 1 | 9.3 | [9 empty] | 0
Schedule 17: Annex 1 | 9.4 | [9 empty] | 0
Schedule 17: Annex 1 | 9.5 | [9 empty] | 0
Schedule 17: Annex 1 | 9.6 | [9 empty] | 0
Schedule 17: Annex 1 | 9.7 | [9 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [9 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [9 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [9 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [9 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [9 empty] | 0
0
Schedule 18 | Introduction | [9 empty] | 0
Schedule 18 | 1 | [9 empty] | 0
Schedule 18 | 1.1 | [9 empty] | 0
Schedule 18 | 1.2 | [9 empty] | 0
Schedule 18 | 1.3 | [9 empty] | 0 | Model reference number and date
Schedule 18 | 1.3A | [9 empty] | 0
Schedule 18 | 1.4 | [9 empty] | 0
Schedule 18 | 1.5 | [9 empty] | 0
Schedule 18 | 1.6 | [9 empty] | 0
Schedule 18 | 1.7 | [9 empty] | 0
Schedule 18 | 1.8 | [9 empty] | 0
Schedule 18 | 1.9 | [9 empty] | 0
Schedule 18 | 2 | [9 empty] | 0
Schedule 18 | 2.1 | [9 empty] | 0
Schedule 18 | 2.2 | [9 empty] | 0
Schedule 18 | 2.3 | [9 empty] | 0
Schedule 18 | 2.4 | [9 empty] | 0
Schedule 18 | 2.5 | [9 empty] | 0
Schedule 18 | 2.6 | [9 empty] | 0
Schedule 18 | 2.7 | [9 empty] | 0
Schedule 18 | 2.8 | [9 empty] | 0
Schedule 18 | 2.9 | [9 empty] | 0
Schedule 18 | 2.1 | [9 empty] | 0
Schedule 18 | 2.11 | [9 empty] | 0
Schedule 18 | 2.12 | [9 empty] | 0
Schedule 18 | 2.13 | [9 empty] | 0
Schedule 18 | 2.14 | [9 empty] | 0
Schedule 18 | 2.15 | [9 empty] | 0
Schedule 18 | 2.16 | [9 empty] | 0
Schedule 18 | 2.17 | [9 empty] | 0
Schedule 18 | 2.18 | [9 empty] | 0
Schedule 18 | 2.19 | [9 empty] | 0
Schedule 18 | 2.2 | [9 empty] | 0
Schedule 18 | 2.21 | [9 empty] | 0
Schedule 18 | 2.22 | [9 empty] | 0
Schedule 18 | 2.23 | [9 empty] | 0
Schedule 18 | 2.24 | [9 empty] | 0
Schedule 18 | 2.25 | [9 empty] | 0
Schedule 18 | 2.26 | [9 empty] | 0
Schedule 18 | 2.27 | [9 empty] | 0
Schedule 18 | 2.28 | [9 empty] | 0
Schedule 18 | 2.29 | [9 empty] | 0
Schedule 18 | 2.3 | [9 empty] | 0
Schedule 18 | 3 | [9 empty] | 0
Schedule 18 | 3.1 | [9 empty] | 0
Schedule 18 | 3.2 | [9 empty] | 0
Schedule 18 | 3.3 | [9 empty] | 0
Schedule 18 | 3.4 | [9 empty] | 0
Schedule 18 | 3.5 | [9 empty] | 0
Schedule 18 | 3.6 | [9 empty] | 0
Schedule 18 | 3.7 | [9 empty] | 0
Schedule 18 | 4 | [9 empty] | 0
Schedule 18 | 4.1 | [9 empty] | 0
Schedule 18 | 5 | [9 empty] | 0
Schedule 18 | 5.1 | [9 empty] | 0
Schedule 18 | 6 | [9 empty] | 0
Schedule 18 | 6.1 | [9 empty] | 0
Schedule 18 | 6.2 | [9 empty] | 0
Schedule 18 | 6.3 | [9 empty] | 0
Schedule 18 | 6.4 | [9 empty] | 0
Schedule 18 | 6.5 | [9 empty] | 0
Schedule 18 | 7 | [9 empty] | 0
Schedule 18 | 7.1 | [9 empty] | 0
Schedule 18 | 8 | [9 empty] | 0
Schedule 18 | 8.1 | [9 empty] | 0
Schedule 18 | 8.2 | [9 empty] | 0
Schedule 18 | 8.3 | [9 empty] | 0
Schedule 18 | 8.4 | [9 empty] | 0
Schedule 18 | 9 | [9 empty] | 0
Schedule 18 | 9.1 | [9 empty] | 0
Schedule 18 | 9.2 | [9 empty] | 0
Schedule 18 | 10 | [9 empty] | 0
Schedule 18 | 10.1 | [9 empty] | 0
Schedule 18 | 10.2 | [9 empty] | 0
Schedule 18 | 10.3 | [9 empty] | 0
Schedule 18 | 10.4 | [9 empty] | 0
Schedule 18 | 10.5 | [9 empty] | 0
Schedule 18 | 11 | [9 empty] | 0
Schedule 18 | 11.1 | [9 empty] | 0
Schedule 18 | 12 | [9 empty] | 0
Schedule 18 | 12.1 | [9 empty] | 0
Schedule 18 | 12.2 | [9 empty] | 0
Schedule 18 | 12.3 | [9 empty] | 0
Schedule 18 | 12.4 | [9 empty] | 0
Schedule 18 | 12.5 | [9 empty] | 0
Schedule 18 | 12.6 | [9 empty] | 0
Schedule 18 | 13 | [9 empty] | 0
Schedule 18 | 13.1 | [9 empty] | 0
Schedule 18 | 13.2 | [9 empty] | 0
Schedule 18 | 13.3 | [9 empty] | 0
Schedule 18 | 13.4 | [9 empty] | 0
Schedule 18 | 14 | [9 empty] | 0
Schedule 18 | 14.1 | [9 empty] | 0
Schedule 18 | 14.2 | [9 empty] | 0
Schedule 18 | 14.3 | [9 empty] | 0
Schedule 18 | 14.4 | [9 empty] | 0
Schedule 18 | 14.5 | [9 empty] | 0
Schedule 18 | 15 | [9 empty] | 0
Schedule 18 | 15.1 | [9 empty] | 0
Schedule 18 | 15.2 | [9 empty] | 0
Schedule 18 | 15.3 | [9 empty] | 0
Schedule 18 | 15.4 | [9 empty] | 0
Schedule 18 | 15.5 | [9 empty] | 0
Schedule 18 | 15.6 | [9 empty] | 0
Schedule 18 | 15.7 | [9 empty] | 0
Schedule 18 | 15.8 | [9 empty] | 0
Schedule 18 | 15.9 | [9 empty] | 0
Schedule 18 | 15.1 | [9 empty] | 0
Schedule 18 | 15.11 | [9 empty] | 0
Schedule 18 | 15.12 | [9 empty] | 0
Schedule 18 | 15.15 | [9 empty] | 0
Schedule 18 | 16 | [9 empty] | 0
Schedule 18 | 16.1 | [9 empty] | 0
Schedule 18 | 16.2 | [9 empty] | 0
Schedule 18 | 16.3 | [9 empty] | 0
Schedule 18 | 16.4 | [9 empty] | 0
Schedule 18 | 16.5 | [9 empty] | 0
Schedule 18 | 16.6 | [9 empty] | 0
Schedule 18 | 16.7 | [9 empty] | 0
Schedule 18 | 16.8 | [9 empty] | 0
Schedule 18 | 16.9 | [9 empty] | 0
Schedule 18 | 16.1 | [9 empty] | 0
Schedule 18 | 17 | [9 empty] | 0
Schedule 18 | 17.1 | [9 empty] | 0
Schedule 18 | 17.2 | [9 empty] | 0
Schedule 18 | 17.3 | [9 empty] | 0
Schedule 18 | 18 | [9 empty] | 0
Schedule 18 | 18.1 | [9 empty] | 0
Schedule 18 | 18.2 | [9 empty] | 0
Schedule 18 | 18.3 | [9 empty] | 0
Schedule 18 | 18.4 | [9 empty] | 0
Schedule 18 | 18.5 | [9 empty] | 0
Schedule 18 | 18.6 | [9 empty] | 0
Schedule 18 | 18.7 | [9 empty] | 0
Schedule 18 | 18.8 | [9 empty] | 0
Schedule 18 | 18.9 | [9 empty] | 0
Schedule 18 | 18.1 | [9 empty] | 0
Schedule 18 | 18.11 | [9 empty] | 0
Schedule 18 | 18.12 | [9 empty] | 0
Schedule 18 | 18.13 | [9 empty] | 0
Schedule 18 | 18.14 | [9 empty] | 0
Schedule 18 | 18.15 | [9 empty] | 0
Schedule 18 | 18.16 | [9 empty] | 0
Schedule 18 | 18.17 | [9 empty] | 0
Schedule 18 | 18.18 | [9 empty] | 0
Schedule 18 | 18.19 | [9 empty] | 0
Schedule 18 | 18.2 | [9 empty] | 0
Schedule 18 | 18.21 | [9 empty] | 0
Schedule 18 | 19 | [9 empty] | 0
Schedule 18 | 19.1 | [9 empty] | 0
Schedule 18 | 19.2 | [9 empty] | 0
Schedule 18 | 19.3 | [9 empty] | 0
Schedule 18 | 19.4 | [9 empty] | 0
Schedule 18 | 19.5 | [9 empty] | 0
Schedule 18 | 19.6 | [9 empty] | 0
Schedule 18 | 19.7 | [9 empty] | 0
Schedule 18 | 19.8 | [9 empty] | 0
Schedule 18 | 19.9 | [9 empty] | 0
Schedule 18 | 19.1 | [9 empty] | 0
Schedule 18 | 19.11 | [9 empty] | 0
Schedule 18 | 20 | [9 empty] | 0
Schedule 18 | 20.1 | [9 empty] | 0
Schedule 18 | 20.2 | [9 empty] | 0
Schedule 18 | 20.3 | [9 empty] | 0
Schedule 18 | 20.4 | [9 empty] | 0
Schedule 18 | 20.5 | [9 empty] | 0
Schedule 18 | 20.6 | [6 empty] | YES |  |  | 1
Schedule 18 | 20.7 | [6 empty] | YES |  |  | 1
Schedule 18 | 20.8 | [9 empty] | 0
Schedule 18 | 20.9 | [6 empty] | YES |  |  | 1
Schedule 18 | 21 | [9 empty] | 0
Schedule 18 | 21.1 | [9 empty] | 0
Schedule 18 | 21.2 | [9 empty] | 0
Schedule 18 | 22 | [9 empty] | 0
Schedule 18 | 22.1 | [9 empty] | 0
Schedule 18 | 22.2 | [9 empty] | 0
Schedule 18 | 22.3 | [9 empty] | 0
Schedule 18 | 22.4 | [9 empty] | 0
Schedule 18 | 23 | [9 empty] | 0
Schedule 18 | 23.1 | [9 empty] | 0
Schedule 18 | 23.2 | [9 empty] | 0
Schedule 18 | 23.3 | [9 empty] | 0
Schedule 18 | 23.4 | [9 empty] | 0
Schedule 18 | 23.5 | [9 empty] | 0
Schedule 18 | 24 | [9 empty] | 0
Schedule 18 | 24.1 | [9 empty] | 0
Schedule 18 | 24.2 | [9 empty] | 0
Schedule 18 | 24.3 | [9 empty] | 0
Schedule 18 | 24.4 | [9 empty] | 0
Schedule 18 | 24.5 | [9 empty] | 0
Schedule 18 | 24.6 | [9 empty] | 0
Schedule 18 | 24.7 | [9 empty] | 0
Schedule 18 | 24.8 | [9 empty] | 0
Schedule 18 | 24.9 | [9 empty] | 0
Schedule 18 | 25 | [9 empty] | 0
Schedule 18 | 25.1 | [9 empty] | 0
Schedule 18 | 25.2 | [9 empty] | 0
Schedule 18 | 25.3 | [9 empty] | 0
Schedule 18 | 25.4 | [9 empty] | 0
Schedule 18 | 25.5 | [9 empty] | 0
Schedule 18 | 25.6 | [9 empty] | 0
Schedule 18 | 25.7 | [9 empty] | 0
Schedule 18 | 25.8 | [9 empty] | 0
Schedule 18 | 25.9 | [9 empty] | 0
Schedule 18 | 25.1 | [9 empty] | 0
Schedule 18 | 25.11 | [9 empty] | 0
Schedule 18 | 25.12 | [9 empty] | 0
Schedule 18 | 25.13 | [9 empty] | 0
Schedule 18 | 25.14 | [9 empty] | 0
Schedule 18 | 25.15 | [9 empty] | 0
Schedule 18 | 25.16 | [9 empty] | 0
Schedule 18 | 25.17 | [9 empty] | 0
Schedule 18 | 25.18 | [9 empty] | 0
Schedule 18 | 25.19 | [9 empty] | 0
Schedule 18 | 26 | [9 empty] | 0
Schedule 18 | 26.1 | [9 empty] | 0
Schedule 18 | 26.2 | [9 empty] | 0
Schedule 18 | 26.3 | [9 empty] | 0
Schedule 18 | 26.4 | [9 empty] | 0
Schedule 18 | 26.5 | [9 empty] | 0
Schedule 18 | 26.6 | [9 empty] | 0
Schedule 18 | 26.7 | [9 empty] | 0
Schedule 18 | 26.8 | [9 empty] | 0
Schedule 18 | 26.9 | [9 empty] | 0
Schedule 18 | 26.1 | [9 empty] | 0
Schedule 18 | 26.11 | [9 empty] | 0
Schedule 18 | 27 | [9 empty] | 0
Schedule 18 | 27.1 | [9 empty] | 0
Schedule 18 | 27.2 | [9 empty] | 0
Schedule 18 | 27.3 | [9 empty] | 0
Schedule 18 | 27.4 | [9 empty] | 0
Schedule 18 | 28 | [9 empty] | 0
Schedule 18 | 28.1 | [9 empty] | 0
Schedule 18 | 28.2 | [9 empty] | 0
Schedule 18 | 29 | [9 empty] | 0
Schedule 18 | 29.1 | [9 empty] | 0
Schedule 18 | 29.2 | [9 empty] | 0
Schedule 18 | 29.3 | [9 empty] | 0
Schedule 18 | 29.4 | [9 empty] | 0
Schedule 18 | 30 | [9 empty] | 0
Schedule 18 | 30.1 | [9 empty] | 0
Schedule 18 | 30.2 | [9 empty] | 0
Schedule 18 | 30.3 | [9 empty] | 0
Schedule 18 | 30.4 | [9 empty] | 0
Schedule 18 | 30.5 | [9 empty] | 0
Schedule 18 | 30.6 | [9 empty] | 0
Schedule 18 | 30.7 | [9 empty] | 0
Schedule 18 | 30.8 | [9 empty] | 0
Schedule 18 | 30.9 | [9 empty] | 0
Schedule 18 | 30.1 | [9 empty] | 0
Schedule 18 | 30.11 | [9 empty] | 0
Schedule 18 | 31 | [9 empty] | 0 | DCP 439 Introduces new Paragraph 31
Schedule 18 | 31.1 | [9 empty] | 0 | DCP 439 Introduces new Paragraph 31.1
Schedule 18: Annex 1 | 1 | [9 empty] | 0
Schedule 18: Annex 1 | 1.1 | [9 empty] | 0
Schedule 18: Annex 1 | 2 | [9 empty] | 0
Schedule 18: Annex 1 | 2.1 | [9 empty] | 0
Schedule 18: Annex 1 | 2.2 | [9 empty] | 0
Schedule 18: Annex 1 | 2.3 | [9 empty] | 0
Schedule 18: Annex 1 | 2.4 | [9 empty] | 0
Schedule 18: Annex 1 | 2.5 | [9 empty] | 0
Schedule 18: Annex 1 | 3 | [9 empty] | 0
Schedule 18: Annex 1 | Definitions | [9 empty] | 0
Schedule 18: Annex 1 | 4 | [9 empty] | 0
Schedule 18: Annex 1 | 4.1 | [9 empty] | 0
Schedule 18: Annex 1 | 4.2 | [9 empty] | 0
Schedule 18: Annex 1 | 4.3 | [9 empty] | 0
Schedule 18: Annex 1 | 4.4 | [9 empty] | 0
Schedule 18: Annex 1 | 4.5 | [9 empty] | 0
Schedule 18: Annex 1 | 4.6 | [9 empty] | 0
Schedule 18: Annex 1 | 4.7 | [9 empty] | 0
Schedule 18: Annex 1 | 4.8 | [9 empty] | 0
Schedule 18: Annex 1 | 4.9 | [9 empty] | 0
Schedule 18: Annex 1 | 5 | [9 empty] | 0
Schedule 18: Annex 1 | 5.1 | [9 empty] | 0
Schedule 18: Annex 1 | 5.2 | [9 empty] | 0
Schedule 18: Annex 1 | 5.3 | [9 empty] | 0
Schedule 18: Annex 1 | 5.4 | [9 empty] | 0
Schedule 18: Annex 1 | 5.5 | [9 empty] | 0
Schedule 18: Annex 1 | 5.6 | [9 empty] | 0
Schedule 18: Annex 1 | 5.7 | [9 empty] | 0
Schedule 18: Annex 1 | 5.8 | [9 empty] | 0
Schedule 18: Annex 1 | 5.9 | [9 empty] | 0
Schedule 18: Annex 1 | 5.1 | [9 empty] | 0
Schedule 18: Annex 1 | 5.11 | [9 empty] | 0
Schedule 18: Annex 1 | 5.12 | [9 empty] | 0
Schedule 18: Annex 1 | 5.13 | [9 empty] | 0
Schedule 18: Annex 1 | 5.14 | [9 empty] | 0
Schedule 18: Annex 1 | 5.15 | [9 empty] | 0
Schedule 18: Annex 1 | 5.16 | [9 empty] | 0
Schedule 18: Annex 1 | 5.17 | [9 empty] | 0
Schedule 18: Annex 1 | 5.18 | [9 empty] | 0
Schedule 18: Annex 1 | 5.19 | [9 empty] | 0
Schedule 18: Annex 1 | 5.2 | [9 empty] | 0
Schedule 18: Annex 1 | 5.21 | [9 empty] | 0
Schedule 18: Annex 1 | 5.22 | [9 empty] | 0
Schedule 18: Annex 1 | 5.23 | [9 empty] | 0
Schedule 18: Annex 1 | 5.24 | [9 empty] | 0
Schedule 18: Annex 1 | 5.25 | [9 empty] | 0
Schedule 18: Annex 1 | 5.26 | [9 empty] | 0
Schedule 18: Annex 1 | 5.27 | [9 empty] | 0
Schedule 18: Annex 1 | 5.28 | [9 empty] | 0
Schedule 18: Annex 1 | 5.29 | [9 empty] | 0
Schedule 18: Annex 1 | 5.3 | [9 empty] | 0
Schedule 18: Annex 1 | 5.31 | [9 empty] | 0
Schedule 18: Annex 1 | 5.32 | [9 empty] | 0
Schedule 18: Annex 1 | 5.33 | [9 empty] | 0
Schedule 18: Annex 1 | 5.34 | [9 empty] | 0
Schedule 18: Annex 1 | 5.35 | [9 empty] | 0
Schedule 18: Annex 1 | 5.36 | [9 empty] | 0
Schedule 18: Annex 1 | 5.37 | [9 empty] | 0
Schedule 18: Annex 1 | 5.38 | [9 empty] | 0
Schedule 18: Annex 1 | 5.39 | [9 empty] | 0
Schedule 18: Annex 1 | 5.4 | [9 empty] | 0
Schedule 18: Annex 1 | 5.41 | [9 empty] | 0
Schedule 18: Annex 1 | 5.42 | [9 empty] | 0
Schedule 18: Annex 1 | 6 | [9 empty] | 0
Schedule 18: Annex 1 | 6.1 | [9 empty] | 0
Schedule 18: Annex 1 | 6.2 | [9 empty] | 0
Schedule 18: Annex 1 | 6.3 | [9 empty] | 0
Schedule 18: Annex 1 | 6.4 | [9 empty] | 0
Schedule 18: Annex 1 | 6.5 | [9 empty] | 0
Schedule 18: Annex 1 | 6.6 | [9 empty] | 0
Schedule 18: Annex 1 | 6.7 | [9 empty] | 0
Schedule 18: Annex 1 | 6.8 | [9 empty] | 0
Schedule 18: Annex 1 | 6.9 | [9 empty] | 0
Schedule 18: Annex 1 | 6.1 | [9 empty] | 0
Schedule 18: Annex 1 | 6.11 | [9 empty] | 0
Schedule 18: Annex 1 | 6.12 | [9 empty] | 0
Schedule 18: Annex 1 | 6.13 | [9 empty] | 0
Schedule 18: Annex 1 | 6.14 | [9 empty] | 0
Schedule 18: Annex 1 | 6.15 | [9 empty] | 0
Schedule 18: Annex 1 | 6.16 | [9 empty] | 0
Schedule 18: Annex 1 | 6.17 | [9 empty] | 0
Schedule 18: Annex 1 | 6.18 | [9 empty] | 0
Schedule 18: Annex 1 | 6.19 | [9 empty] | 0
Schedule 18: Annex 1 | 6.2 | [9 empty] | 0
Schedule 18: Annex 1 | 6.21 | [9 empty] | 0
Schedule 18: Annex 1 | 6.22 | [9 empty] | 0
Schedule 18: Annex 1 | 6.23 | [9 empty] | 0
Schedule 18: Annex 1 | 6.24 | [9 empty] | 0
Schedule 18: Annex 1 | 6.25 | [9 empty] | 0
Schedule 18: Annex 1 | 6.26 | [9 empty] | 0
Schedule 18: Annex 1 | 6.27 | [9 empty] | 0
Schedule 18: Annex 1 | 6.28 | [9 empty] | 0
Schedule 18: Annex 1 | 6.29 | [9 empty] | 0
Schedule 18: Annex 1 | 6.3 | [9 empty] | 0
Schedule 18: Annex 1 | 6.31 | [9 empty] | 0
Schedule 18: Annex 1 | 6.32 | [9 empty] | 0
Schedule 18: Annex 1 | 6.33 | [9 empty] | 0
Schedule 18: Annex 1 | 6.34 | [9 empty] | 0
Schedule 18: Annex 1 | 7 | [9 empty] | 0
Schedule 18: Annex 1 | 7.1 | [9 empty] | 0
Schedule 18: Annex 1 | 7.2 | [9 empty] | 0
Schedule 18: Annex 1 | 7.3 | [9 empty] | 0
Schedule 18: Annex 1 | 7.4 | [9 empty] | 0
Schedule 18: Annex 1 | 7.5 | [9 empty] | 0
Schedule 18: Annex 1 | 8 | [9 empty] | 0
Schedule 18: Annex 1 | 8.1 | [9 empty] | 0
Schedule 18: Annex 1 | 8.2 | [9 empty] | 0
Schedule 18: Annex 1 | 8.3 | [9 empty] | 0
Schedule 18: Annex 1 | 8.4 | [9 empty] | 0
Schedule 18: Annex 1 | 8.5 | [9 empty] | 0
Schedule 18: Annex 1 | 8.6 | [9 empty] | 0
Schedule 18: Annex 1 | 8.7 | [9 empty] | 0
Schedule 18: Annex 1 | 8.8 | [9 empty] | 0
Schedule 18: Annex 1 | 8.9 | [9 empty] | 0
Schedule 18: Annex 1 | 8.1 | [9 empty] | 0
Schedule 18: Annex 1 | 8.11 | [9 empty] | 0
Schedule 18: Annex 1 | 8.12 | [9 empty] | 0
Schedule 18: Annex 1 | 8.13 | [9 empty] | 0
Schedule 18: Annex 1 | 8.14 | [9 empty] | 0
Schedule 18: Annex 1 | 8.15 | [9 empty] | 0
Schedule 18: Annex 1 | 8.16 | [9 empty] | 0
Schedule 18: Annex 1 | 8.17 | [9 empty] | 0
Schedule 18: Annex 1 | 8.18 | [9 empty] | 0
Schedule 18: Annex 1 | 8.19 | [9 empty] | 0
Schedule 18: Annex 1 | 8.2 | [9 empty] | 0
Schedule 18: Annex 1 | 8.21 | [9 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [9 empty] | 0
Schedule 18: Annex 1 | Attachment 2 | [9 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [9 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [9 empty] | 0
0
Schedule 20 | Introduction | [9 empty] | 0
Schedule 20 | 1.1 | [9 empty] | 0
Schedule 20 | 2.1 | [9 empty] | 0
Schedule 20 | 3.1 | [9 empty] | 0
Schedule 20 | 3.2 | [9 empty] | 0
0
Schedule 29 | Introduction | [9 empty] | 0
Schedule 29 | 1 | [9 empty] | 0
Schedule 29 | 1A | [9 empty] | 0
Schedule 29 | 2 | [9 empty] | 0
Schedule 29 | 3 | [9 empty] | 0
Schedule 29 | 4 | [9 empty] | 0
Schedule 29 | 5 | [9 empty] | 0
Schedule 29 | 6 | [9 empty] | 0
Schedule 29 | 7 | [9 empty] | 0
Schedule 29 | 8 | [9 empty] | 0
Schedule 29 | 9 | [9 empty] | 0
Schedule 29 | 10 | [9 empty] | 0
Schedule 29 | 11 | [9 empty] | 0
Schedule 29 | 11A | [9 empty] | 0
Schedule 29 | 12 | [9 empty] | 0
Schedule 29 | 13 | [9 empty] | 0
Schedule 29 | 14 | [9 empty] | 0
Schedule 29 | 15 | [9 empty] | 0
Schedule 29 | 16 | [9 empty] | 0
Schedule 29 | 17 | [9 empty] | 0
Schedule 29 | 18 | [9 empty] | 0
Schedule 29 | 19 | [9 empty] | 0
Schedule 29 | 20 | [9 empty] | 0
Schedule 29 | 21 | [9 empty] | 0
Schedule 29 | 22 | [9 empty] | 0
Schedule 29 | 23 | [9 empty] | 0
Schedule 29 | 24 | [9 empty] | 0
Schedule 29 | 25 | [9 empty] | 0
Schedule 29 | 26 | [9 empty] | 0
Schedule 29 | 27 | [9 empty] | 0
Schedule 29 | 28 | [9 empty] | 0
Schedule 29 | 29 | [9 empty] | 0
Schedule 29 | 30 | [9 empty] | 0
Schedule 29 | 31 | [9 empty] | 0
Schedule 29 | 32 | [9 empty] | 0
Schedule 29 | 33 | [9 empty] | 0
Schedule 29 | 34 | [9 empty] | 0
Schedule 29 | 35 | [9 empty] | 0
Schedule 29 | 36 | [9 empty] | 0
Schedule 29 | 37 | [9 empty] | 0
Schedule 29 | 38 | [9 empty] | 0
Schedule 29 | 39 | [9 empty] | 0
Schedule 29 | 40 | [9 empty] | 0
Schedule 29 | 41 | [9 empty] | 0
Schedule 29 | 42 | [9 empty] | 0
Schedule 29 | 43 | [9 empty] | 0
Schedule 29 | 44 | [9 empty] | 0
Schedule 29 | 45 | [9 empty] | 0
Schedule 29 | 46 | [9 empty] | 0
Schedule 29 | 46A | [9 empty] | 0
Schedule 29 | 47 | [9 empty] | 0
0
Schedule 32 | 1 | [9 empty] | 0
Schedule 32 | 1.1 | [9 empty] | 0
Schedule 32 | 1.2 | [9 empty] | 0
Schedule 32 | 1.2A | [9 empty] | 0
Schedule 32 | 1.3 | [9 empty] | 0
Schedule 32 | 1.4 | [9 empty] | 0
Schedule 32 | 1.5 | [9 empty] | 0
Schedule 32 | 1.6 | [9 empty] | 0
Schedule 32 | 1.7 | [9 empty] | 0
Schedule 32 | 1.8 |  | YES | [7 empty] | 1
Schedule 32 | 1.9 | [9 empty] | 0
Schedule 32 | 1.10 |  | YES | [7 empty] | 1
Schedule 32 | 2 | [9 empty] | 0
Schedule 32 | 2.1 | [9 empty] | 0
Schedule 32 | 2.2 | [9 empty] | 0
Schedule 32 | 2.3 | [9 empty] | 0
Schedule 32 | 2.4 | [9 empty] | 0
Schedule 32 | 2.5 | [9 empty] | 0
Schedule 32 | 3 | [9 empty] | 0
Schedule 32 | 3.1 |  | YES | [7 empty] | 1
Schedule 32 | 3.2 | [9 empty] | 0
Schedule 32 | 3.3 | [9 empty] | 0
Schedule 32 | 3.4 | [9 empty] | 0
Schedule 32 | 3.5 | [9 empty] | 0
Schedule 32 | 3.6 | [9 empty] | 0
Schedule 32 | 4 | [9 empty] | 0
Schedule 32 | 4.1 |  | YES | [7 empty] | 1
Schedule 32 | 4.2 |  | YES | [7 empty] | 1
Schedule 32 | 4.2A |  | YES | [7 empty] | 1
Schedule 32 | 4.3 | [9 empty] | 0
Schedule 32 | 4.4 | [9 empty] | 0
Schedule 32 | 4.5 |  | YES | [7 empty] | 1
Schedule 32 | 4.6 | [9 empty] | 0
Schedule 32 | 5 | [9 empty] | 0
Schedule 32 | 5.1 | [9 empty] | 0
Schedule 32 | 5.2 | [9 empty] | 0
Schedule 32 | 5.3 | [9 empty] | 0
Schedule 32 | 5A. |  | YES | [7 empty] | 1
Schedule 32 | 5A.1 | [9 empty] | 0
Schedule 32 | 5A.1A | [9 empty] | 0
Schedule 32 | 5A.2 | [9 empty] | 0
Schedule 32 | 6 | [9 empty] | 0
Schedule 32 | 6.1 |  |  | YES | [6 empty] | 1
Schedule 32 | 6.2 |  |  | YES | [6 empty] | 1
Schedule 32 | 6.3 |  | YES | [7 empty] | 1
Schedule 32 | 6.4 | [9 empty] | 0
Schedule 32 | 6.4A | [9 empty] | 0
Schedule 32 | 6.5 |  | YES | [7 empty] | 1
Schedule 32 | 6.6 | [9 empty] | 0
Schedule 32 | 6.7 | [9 empty] | 0
Schedule 32 | 6.8 | [9 empty] | 0
Schedule 32 | 6.9 | [9 empty] | 0
Schedule 32 | 6.10 | [9 empty] | 0
Schedule 32 | 6.11 | [9 empty] | 0
Schedule 32 | 6.12 | [9 empty] | 0
Schedule 32 | 7 | [9 empty] | 0
Schedule 32 | 7.1 | [9 empty] | 0
Schedule 32 | 7.2 | [9 empty] | 0
Schedule 32 | 7.3 | [9 empty] | 0
Schedule 32 | 7.4 | [9 empty] | 0
Schedule 32 | 7.5 | [9 empty] | 0
Schedule 32 | 7.6 | [9 empty] | 0
Schedule 32 | 7.7 | [9 empty] | 0
Schedule 32 | 7.8 | [9 empty] | 0
Schedule 32 | 7.9 | [9 empty] | 0
Schedule 32 | 7.1 | [9 empty] | 0
Schedule 32 | 7.11 | [9 empty] | 0
Schedule 32 | 7.12 | [9 empty] | 0
Schedule 32 | 7.13 | [9 empty] | 0
Schedule 32 | 7.14 | [9 empty] | 0
Schedule 32 | 7.15 | [9 empty] | 0
Schedule 32 | 7.16 | [9 empty] | 0
Schedule 32 | 7.17 | [9 empty] | 0
Schedule 32 | 8 | [9 empty] | 0
Schedule 32 | 8.1 | [9 empty] | 0
Schedule 32 | 8.2 | [9 empty] | 0
Schedule 32 | Definitions |  | YES | YES | [6 empty] | 2
Charging Methodology CPs Legal Text Overlap Tracker