## CPs
| CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Current Status | Status Changed in the last month | Date Issued to Ofgem | Original Expected Decision Date | Latest Expected Decision Date
STATUS - INITIAL ASSESSMENT
N/A
STATUS - DEFINITION
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Andrew Malley | 14/04/2021 | 17 | Yes - See comments in status column | TBC | The Working Group met on 02 October to review the need for a BSC change. It was agreed that a BSC change was required and that DCP 388 couldn’t be progressed until the BSC modification had been defined so DCP 388 has been paused until the Proposer raises the required BSC modification.
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | This change seeks to ensure that all DCUSA Parties, that de-energise metering equipment as part of any planned work, provide the Distributor with advance notification of the supply interruption. | General | 1 | Melissa Kendal / Richard Colwill | TBC | 2023-03-06 | 15 | No | Next scheduled release following approval | This CP is on hold pending confirmation from the Proposer as to whether they wish to continue to progress DCP 419 following Ofgem's decision on the related REC change. | #REF!
DCP 420 | Provide targeted relief from residual charges for electric vehicle charging sites | The intent of this Change Proposal is to provide targeted relief from residual charges to publicly accessible electric vehicle (“EV”) charging sites. This may be a temporary fix to be put in place until the charging stations included are commercially viable. | General | 1 | Craig Booth / Richard Colwill | Thomas Holderness | 2023-03-29 | 19 | Yes - See comments in status column | TBC | The DCUSA Secretariat completed an initial draft of an impact assessment and presented this to the Working Group. The Working Group identified a number of actions required to make the analysis robust and fit for purpose. These actions are being progressed offline and the next meeting will be arrange via a poll. A NESO representative has offered to provide help in understanding the TNUoS impacts of this CP, however it has been challenging to identify a convenient time to meet to complete the work. This is being progress as a matter of priority. | #REF!
DCP 424 | Use of System charging for complex sites | This change proposal enables the correct DUoS to be paid by meters that are class F or G within a Class 5 or Class 6 Complex Site as described in BSC Modification P441 (where netting of Import and Export takes place for BSC Settlement purposes) in a practical manner. Under p441 where generation and demand are netted before settlement, the gross values must be added to the D0036 or D0275 to ensure the correct DUoS is charged. However, for class F and G the MPAN counts are included on the D0030 data flows but the volumes are zero. In order for the volumes to be correctly charged DUoS it is proposed that these volumes are included in the D0036 or D0275 using a pseudo MPAN for the gross value. | CDCM | 1 | Andy Green / Craig Booth | TBC | 2023-10-05 | 11 | No | Aligned to BSC Mod P441 Implementation Date | The Working Group met on 12 May 2026 and agreed on the legal text for consultion and to review the consultation document. The consultation is due to be issued W/C 19 May 2026
DCP 442 | Aligning enduring flexible connections | The intent of this Change Proposal is to align (and clarify) the two approaches that currently may result in a flexible connection being provided on an enduring basis. A flexible connection on an enduring basis is an arrangement that allows a Customer’s import/export of electricity via a connection to be restricted by a DNO/IDNO Party in perpetuity. This CP proposes that such a connection shall be a Flexible Connection rather than a Curtailable Connection. | General | 1 | Melissa Kendal / Craig Booth | TBC | 2024-07-01 | 7 | Yes - See comments in status column | TBC | The next Working Group is currently TBC - due to the Proposer's availability. Once the next meeting has been scheduled, the aim is to finalise the draft Consultation ready to issue to wider industry. | DEFINITION
DCP 443 | Excess Capacity | The purpose of this Change Proposal is to drive the correct customer behaviour regarding exceeding capacity. | CDCM / EDCM | 1 | Melissa Kendal / Andy Green | TBC | 2024-09-07 | 16 | No | 2026-01-04 | A poll has been issued to Working Group members to determine the date of the next meeting where the second consultaion document will be reviewed.
DCP 446 | Emergency Disconnections | To enable distributors to charge customers covered by section 2 of the National Terms of Connection for emergency disconnections that have been caused by their act or omission. | General | 1 | Hannah Proffitt / Craig Booth | N/A | 2024-11-07 | 5 | No | Next scheduled release following approval | The DCP 446 Working Group met on 01 April and plan to meet again on 14 April. They will look at resubmitting the Change Report shortly. | AWAITING AUTHORITY CONSENT |  | 2025-04-17
DCP 454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | The intent of this CP is to provide enduring targeted relief from residual charges to publicly accessible electric vehicle (“EV”) charging sites. | CDCM | 1 | Craig Booth / Richard Colwill | Thomas Holderness | 2025-05-06 | 1 | Yes - See comments in status column | 2028-04-01 | The DCUSA Secretariat completed an initial draft of an impact assessment and presented this to the DCP 420 Working Group. The same impact assessment will form the basis of the impact assessment for DCP 454, but will be amended. The DCP 420 update is therefore relevant to this. | #REF!
DCP 461 | Reducing the Impact of Transmission Distribution Charges | This Change Proposal seeks to address a growing set of structural, economic, and policy misalignments that are actively hindering the UK’s energy transition. | CCCM | 1 | Melissa Kendal / Craig Booth | N/A | 2025-08-13 | 14 | No | TBC | The DCP 461 consultation was issued on 6 May, with a deadline for responses set at 29 May. The next meeting is scheduled for 18 June.
DCP 464 | IDNO Connection Applications: Treatment of Existing Assets | The intent of this Change Proposal is to clarify and align the DNO approach to the charging methodology applied to network asset(s) for IDNO applications when the IDNO is the sole user of specific network asset(s). | General | 1 | Melissa Kendal / Andy Green | N/A | 2025-09-08 | 6 | No | 2026-04-01 | The Working Group agreed that further support from the legal advisors is needed and a poll has been issued to agree the next meeting date where the Working Group will review updated examples for this CP
DCP 465 | NFD Generator and Battery Capacity Charges | The CDCM differs from the EDCM in that it does not treat generation sites differently to demand sites when determining the Capacity charge. This change proposal is to align The Differential In Generator and Battery Capacity charges between the two methodologies and therefore reduce the capacity charges for CDCM Generators and Batteries. | CDCM | 1 | Melissa Kendal / Craig Booth | TBC | 2025-10-15 | 2 | No | 2028-04-01 | The Working Group are currently finalising a consultation document and plan to issue it to industry shortly.
DCP 467 | Online reporting tools for Category A and B defects | To mandate that relevant DCUSA Parties utilise online reporting tools where DNOs have made them available for the purpose of reporting Category A and B situations. | General | 2 | Hannah Proffitt / Richard Colwill | TBC | 2025-12-10 | 1 | No | TBC | The Working Group issued a consultation on 27 April, with a deadline for responses set at 19 May. The next meeting is scheduled for 27 May 2026 to review the responses to the consultation. |  | CONSULTATION
DCP 469 | Cross Code Standardisation of Charging Arrangement Notice Periods | Cross Code standardisation of Charging Arrangement Notice Periods. | General | 1 | Melissa Kendal / Richard Colwill |  |  | 1 | No | 2026-09-30 | The DCP 469 Working Group issued an RFI on 16 April, with a deadline for responses set at 11 May. The next meeting is scheduled for 21 May 2026, where the Working Group will review the responses to the RFI. |  | RFI
DCP 473 | Non-consuming De-energised CT-Metered sites | To provide mechanisms for distributors to deal effectively with long term non-consuming CT-metered de-energised sites | General | 1 | Hannah Proffit / Andy Green | N/A | 2026-04-15 | 2 | No | 2028-04-01 | A Working Group meeting has been set up for 13 May 2026 to review the draft consultation document with the intent being to issue the consultaion out on the week commencing 18 May 2026. |  | DEFINITION
STATUS - CHANGE REPORT
DCP 468 | Remove Redundant DataFlow from DTC/EMDS | D0164 / MM00069 might be a redundant relic from 1998. The Proposer can find no current obligation, nor any right, under DCUSA which would either be discharged or exercised (respectively) by its use. If no longer required, any such redundant data flows should be removed from DTC/EMDS. | General | 2 | Melissa Kendal / Craig Booth | N/A |  | 2 | No | 2026-11-05 | The DCP 468 Change Report will be issued to the May Panel meeting. |  | CHANGE REPORT
DCP 466 | Tariff Band to Follow Capacity | To ensure tariff bands for HH settled sites are aligned to a customer’s capacity at all times (e.g. tariff bands are assessed/changed whenever a capacity change is agreed.) | General | 1 | Melissa Kendal / Richard Colwill | TBC | 23/10.2025 | 5 | No | first day of the second month following Authority approval | The DCP 466 Working Group is aiming to present the Change Report at the May Panel meeting. |  | CHANGE REPORT
STATUS - VOTING
N/A
STATUS - AWAITING AUTHORITY CONSENT
DCP 412 | Allocation of banding for TCR Charges for ‘Peaky’ Final Demand Customers | The intent of this CP is to consider the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Craig Booth / Richard Colwill | Andrew Malley | 2022-10-11 | 39 | No | 10 Working Days following Authority Decision | The Working Group have finalised the change report and legal text and this is being tabled at the February Panel. DCP 412 was approved by the Panel during their meeting in February and subsequently issued to Parties for voting on 20 February 2025, with a deadline of 13 March 2025. A Change Declaration was issued to both Parties and Ofgem on 19 March 2025. The Authority has seen been in touch to request the Secretariat conducts additional work on the impact assessment (this is not a send back). | AWAITING AUTHORITY CONSENT |  | 2025-03-19 | TBC
DCP 452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | The intent of this Change Proposal is to correct an oversight in DCUSA which results in customers connecting directly to Grid Supply Point incorrectly facing a locational FCP charge relating to assets downstream of their connection. | EDCM | 1 | George Kestner / Dylan Townsend | Thomas Holderness | 2025-02-28 | 12 | No | 2028-04-01 | The Change Report was issued to the March Panel for approval to be issued for voting. During the March Panel meeting, the Panel approved for DCP 452 to be issued for voting for a period of 15 Working Days commencing on 19 March 2026. Following the Party voting period, a Change Declaration was issued to the Authroity on 22 April 2026 that presented a reccomendation from Parties that DCP 452 be approved. | DEFINITION | AWAITING AUTHORITY CONSENT | 2025-04-22 | TBC
STATUS - AWAITING IMPLEMENTATION
2026-05-18
DCP 472 | DCMDG & SIG Agenda Timings | The purpose of this Change Proposal is to amend the DCUSA so that the Secretariat circulates DCMDG & SIG agendas for each meeting at least 5 Working Days in advance. | General | 2 | Craig Booth | N/A | 2026-02-20 | N/A | No | 2026-05-18 | The Panel approved for DCP 472 to progress directly to the Change Report phase as a Part 2 Matter during their March 2026 Panel meeting and the Change Report was presented to the Panel during the April Panel meeting where the Panel approved for it to be issued for Party voting. Party voting closed on 08 May 2026, and a Change Declaration was subsequently issued, confirming that Parties had approved both the solution and implementation date. |  | AWAITING IMPLEMENTATION
2026-06-25
DCP 471 | Lead Time For DCPs | The purpose of this Change Proposal is to ensure that a lead time of 8 working days is given for changes to reach the next Panel meeting. | General | 2 | Craig Booth | N/A | 2026-02-22 | N/A | No | 2026-06-25 | The Panel approved for DCP 471 to progress directly to the Change Report phase as a Part 2 Matter during their March 2026 Panel meeting and the Change Report was presented to the Panel during the April Panel meeting where the Panel approved for it to be issued for Party voting. Party voting closed on 08 May 2026, and a Change Declaration was subsequently issued, confirming that Parties had approved both the solution and implementation date. |  | AWAITING IMPLEMENTATION
DCP 470 | Independent Credit Assessments | The purpose of this Change Proposal is to allow the Company to apply an independent credit assessment where a User has not requested it. | General | 2 | Melissa Kendal / Andy Green |  |  | 3 | No | 2026-06-25 | The Working Group issued their Change Report to the Panel during the April Panel meeting where the Panel approved for it to be issued for Party voting. Party voting closed on 08 May 2026, and a Change Declaration was subsequently issued, confirming that Parties had approved both the solution and implementation date. |  | AWAITING IMPLEMENTATION
2026-11-11
DCP 459 | DNO invoices to Embedded DNO | The intent of the Change Proposal is to require separate invoice backing data to be provided by DNO Parties when issuing invoices to EDNOs. | General | 3 | Hannah Proffitt / Andy Green | N/A | 2025-08-01 | 4 | No | 2026-11-11 | The Working Group issued their Change Report to the Panel during the April Panel meeting where the Panel approved for it to be issued for Party voting. Party voting closed on 08 May 2026, and a Change Declaration was subsequently issued, confirming that Parties had approved both the solution and implementation date. |  | AWAITING IMPLEMENTATION
2027-04-01
DCP 440 | Consuming “de-energised” sites | To ensure all consuming “de-energised” sites are charged DUoS. | CDCM | 1 | Hannah Proffitt / Andy Green | Shaun McRaith | 2024-03-14 | 10 | No | 2027-04-01 | On 29 August 2025, Ofgem issued their decision to approve DCP 456. DCP 440 will be implemented on 01/04/2027.
DCP 450 | Managing the effects of surplus residual charge in the CDCM | To determine the appropriate arrangements for managing the effects of large residual values in the CDCM. | CDCM | 1 | Hannah Proffitt / Craig Booth | James Harvey | 2025-02-10 | 3 | No | 2027-04-01 | On 20 October 2025, Ofgem published their decision to accept DCP 450. The Change is now awaiting implementation. DCP 450 will be implemented on 01/04/2027.
STATUS - SENT BACK
N/A
STATUS - IMPLEMENTED
N/A
STATUS - REJECTED
N/A
STATUS - WITHDRAWN
DCP 463 | Charging non-consuming De-energised CT-Metered sites | This Change Proposal seeks to charge DUoS fixed and capacity charges to non-consuming CT-metered de-energised sites. | CCCM | 1 | Hannah Proffitt / Andy Green | N/A | 2025-09-05 | 7 | No | 2027-04-01 | The Working Group met on 7 April to refine the solution options and to consider the legal text and second consultation. The group noted that as the Panel decided it would not be possible to extend the scope of the CP, a new CP has been raised and will be presented for initial assessment at the April Panel. The current WG will remain in place for the new CP and the next meeting will be held on 29 April. |  | WITHDRAWN
Change Register - May 2026

## Status Changes
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status | Status Changed in the last month
DCP 467 | Online reporting tools for Category A and B defects | To mandate that relevant DCUSA Parties utilise online reporting tools where DNOs have made them available for the purpose of reporting Category A and B situations. | General | 2 | Hannah Proffitt / Richard Colwill | TBC | 2025-12-10 | 1 | No | TBC | The Working Group issued a consultation on 27 April, with a deadline for responses set at 19 May. The next meeting is scheduled for 27 May 2026 to review the responses to the consultation. | 0 | CONSULTATION
DCP 469 | Cross Code Standardisation of Charging Arrangement Notice Periods | Cross Code standardisation of Charging Arrangement Notice Periods. | General | 1 | Melissa Kendal / Richard Colwill | 0 | 0 | 1 | No | 46295 | The DCP 469 Working Group issued an RFI on 16 April, with a deadline for responses set at 11 May. The next meeting is scheduled for 21 May 2026, where the Working Group will review the responses to the RFI. | 0 | RFI
DCP 473 | Non-consuming De-energised CT-Metered sites | To provide mechanisms for distributors to deal effectively with long term non-consuming CT-metered de-energised sites | General | 1 | Hannah Proffit / Andy Green | N/A | 2026-04-15 | 2 | No | 2028-04-01 | A Working Group meeting has been set up for 13 May 2026 to review the draft consultation document with the intent being to issue the consultaion out on the week commencing 18 May 2026. | 0 | DEFINITION
DCP 468 | Remove Redundant DataFlow from DTC/EMDS | D0164 / MM00069 might be a redundant relic from 1998. The Proposer can find no current obligation, nor any right, under DCUSA which would either be discharged or exercised (respectively) by its use. If no longer required, any such redundant data flows should be removed from DTC/EMDS. | General | 2 | Melissa Kendal / Craig Booth | N/A | 0 | 2 | No | 46331 | The DCP 468 Change Report will be issued to the May Panel meeting. | 0 | CHANGE REPORT
DCP 466 | Tariff Band to Follow Capacity | To ensure tariff bands for HH settled sites are aligned to a customer’s capacity at all times (e.g. tariff bands are assessed/changed whenever a capacity change is agreed.) | General | 1 | Melissa Kendal / Richard Colwill | TBC | 23/10.2025 | 5 | No | first day of the second month following Authority approval | The DCP 466 Working Group is aiming to present the Change Report at the May Panel meeting. | 0 | CHANGE REPORT
DCP 452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | The intent of this Change Proposal is to correct an oversight in DCUSA which results in customers connecting directly to Grid Supply Point incorrectly facing a locational FCP charge relating to assets downstream of their connection. | EDCM | 1 | George Kestner / Dylan Townsend | Thomas Holderness | 2025-02-28 | 12 | No | 46844 | The Change Report was issued to the March Panel for approval to be issued for voting. During the March Panel meeting, the Panel approved for DCP 452 to be issued for voting for a period of 15 Working Days commencing on 19 March 2026. Following the Party voting period, a Change Declaration was issued to the Authroity on 22 April 2026 that presented a reccomendation from Parties that DCP 452 be approved. | DEFINITION | AWAITING AUTHORITY CONSENT
DCP 472 | DCMDG & SIG Agenda Timings | The purpose of this Change Proposal is to amend the DCUSA so that the Secretariat circulates DCMDG & SIG agendas for each meeting at least 5 Working Days in advance. | General | 2 | Craig Booth | N/A | 2026-02-20 | N/A | No | 46160 | The Panel approved for DCP 472 to progress directly to the Change Report phase as a Part 2 Matter during their March 2026 Panel meeting and the Change Report was presented to the Panel during the April Panel meeting where the Panel approved for it to be issued for Party voting. Party voting closed on 08 May 2026, and a Change Declaration was subsequently issued, confirming that Parties had approved both the solution and implementation date. | 0 | AWAITING IMPLEMENTATION
DCP 471 | Lead Time For DCPs | The purpose of this Change Proposal is to ensure that a lead time of 8 working days is given for changes to reach the next Panel meeting. | General | 2 | Craig Booth | N/A | 2026-02-22 | N/A | No | 46198 | The Panel approved for DCP 471 to progress directly to the Change Report phase as a Part 2 Matter during their March 2026 Panel meeting and the Change Report was presented to the Panel during the April Panel meeting where the Panel approved for it to be issued for Party voting. Party voting closed on 08 May 2026, and a Change Declaration was subsequently issued, confirming that Parties had approved both the solution and implementation date. | 0 | AWAITING IMPLEMENTATION
DCP 470 | Independent Credit Assessments | The purpose of this Change Proposal is to allow the Company to apply an independent credit assessment where a User has not requested it. | General | 2 | Melissa Kendal / Andy Green | 0 | 0 | 3 | No | 46198 | The Working Group issued their Change Report to the Panel during the April Panel meeting where the Panel approved for it to be issued for Party voting. Party voting closed on 08 May 2026, and a Change Declaration was subsequently issued, confirming that Parties had approved both the solution and implementation date. | 0 | AWAITING IMPLEMENTATION
DCP 459 | DNO invoices to Embedded DNO | The intent of the Change Proposal is to require separate invoice backing data to be provided by DNO Parties when issuing invoices to EDNOs. | General | 3 | Hannah Proffitt / Andy Green | N/A | 2025-08-01 | 4 | No | 46337 | The Working Group issued their Change Report to the Panel during the April Panel meeting where the Panel approved for it to be issued for Party voting. Party voting closed on 08 May 2026, and a Change Declaration was subsequently issued, confirming that Parties had approved both the solution and implementation date. | 0 | AWAITING IMPLEMENTATION
DCP 463 | Charging non-consuming De-energised CT-Metered sites | This Change Proposal seeks to charge DUoS fixed and capacity charges to non-consuming CT-metered de-energised sites. | CCCM | 1 | Hannah Proffitt / Andy Green | N/A | 2025-09-05 | 7 | No | 46478 | The Working Group met on 7 April to refine the solution options and to consider the legal text and second consultation. The group noted that as the Panel decided it would not be possible to extend the scope of the CP, a new CP has been raised and will be presented for initial assessment at the April Panel. The current WG will remain in place for the new CP and the next meeting will be held on 29 April. | 0 | WITHDRAWN
Status Change - May 2026

## Timetables
DCP | Title | Part 1/ Part 2 Matter | Timetable Change | May | Jun | Jul | Aug | Sep | Oct
473 | Non-consuming De-energised CT-Metered sites | Part 1 | N | DEF | DEF | CON | DEF | DEF | CR
469 | Cross Code Standardisation of Charging Arrangement Notice Periods | Part 1 | Y | May: DEF; Jun: CR
Timetable Change |  |  |  | DEF | CON | DEF | DEF | CR
468 | Remove Redundant DataFlow from DTC/EMDS | Part 2 | N | bar: May
467 | Online reporting tools for Category A and B defects | Part 1 | N | May: DEF; Jun: CR
466 | To ensure tariff bands for HH settled sites are aligned to a customer’s capacity at all times (e.g. tariff bands are assessed/changed whenever a capacity change is agreed.) | Part 1 | N | bar: May
465 | NFD Generator and Battery Capacity Charges | Part 1 | N | CON | DEF | DEF | DEF | CR
464 | IDNO Connection Applications: Treatment of Existing Assets | Part 1 | Y | bar: May
Timetable Change |  |  |  | May: DEF; Jun: DEF; Jul: CR
461 | Reducing the Impact of Transmission Distribution Charges | Part 1 | N | May: DEF; Jun: DEF; Jul: CR
454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | Part 1 | Y | May: DEF; Jun: DEF; Jul: CR
Timetable Change |  |  |  | DEF | CON | DEF | DEF | CR
443 | Excess Capacity | Part 1 | Y | bar: May
Timetable Change |  |  |  | May: DEF; Jun: DEF; Jul: CR
442 | Aligning enduring flexible connections | Part 1 | N | May: DEF
424 | Use of System charging for complex sites | Part 1 | N | May: DEF; Jun: CR
420 | Include Car Charging Stations In The Definition For Non Final Demand | Part 1 | Y | bar: May
Timetable Change |  |  |  | DEF | CON | DEF | DEF | CR
388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | Part 1 | N | May: O/H
| DEFINITION | DEF
| RFI | RFI
| CONSULTATION | CON/ CON 2
| CHANGE REPORT | CR
| ON HOLD | O/H

## Legal Text Overlap Tracker
YES
|  | DCP 424 | DCP 388 | DCP 412 | DCP 420 | DCP 440 | DCP 450 | DCP 443 | DCP 463 | DCP 452
|  | 2026-12-31 | 2027-01-18 | TBC | 2026-11-01 | 2027-04-01 | 2027-04-01 | 2026-04-01 | 2027-04-01 | 2028-04-01 |  | NOTES TO ASSIST
Schedules | Paragraph Number | Definition | On Hold | Awaiting Consent | Definition | Awaiting Implementation | Awaiting Implementation | Definition | Definition | Change Report | Number of CPs Impacting Paragraph
Schedule 15 | - | [9 empty] | 0
0
Schedule 16 | Introduction | [9 empty] | 0
Schedule 16 | 1 | [9 empty] | 0
Schedule 16 | 2 | [9 empty] | 0
Schedule 16 | 3 | [9 empty] | 0
Schedule 16 | 4 | [9 empty] | 0
Schedule 16 | 5 | [9 empty] | 0
Schedule 16 | 6 | [9 empty] | 0
Schedule 16 | 7 | [9 empty] | 0
Schedule 16 | 7A | [9 empty] | 0
Schedule 16 | 8 | [9 empty] | 0
Schedule 16 | 9 | [9 empty] | 0
Schedule 16 | 10 | [9 empty] | 0
Schedule 16 | 10A | [9 empty] | 0
Schedule 16 | 11 | [9 empty] | 0
Schedule 16 | 12 | [9 empty] | 0
Schedule 16 | 13 | [9 empty] | 0
Schedule 16 | 14 | [9 empty] | 0
Schedule 16 | 15 | [9 empty] | 0
Schedule 16 | 16 | [9 empty] | 0
Schedule 16 | 17 | [9 empty] | 0
Schedule 16 | 18 | [9 empty] | 0
Schedule 16 | 19 | [9 empty] | 0
Schedule 16 | 20 | [9 empty] | 0
Schedule 16 | 21 | [9 empty] | 0
Schedule 16 | 22 | [9 empty] | 0
Schedule 16 | 23 | [9 empty] | 0
Schedule 16 | 24 | [9 empty] | 0
Schedule 16 | 25 | [9 empty] | 0
Schedule 16 | 26 | [9 empty] | 0
Schedule 16 | 27 | [9 empty] | 0
Schedule 16 | 28 | [9 empty] | 0
Schedule 16 | 29 | [9 empty] | 0
Schedule 16 | 30 | [9 empty] | 0
Schedule 16 | 31 | [9 empty] | 0
Schedule 16 | 32 | [9 empty] | 0
Schedule 16 | 33 | [9 empty] | 0
Schedule 16 | 34 | [9 empty] | 0
Schedule 16 | 35 | [9 empty] | 0
Schedule 16 | 36 | [9 empty] | 0
Schedule 16 | 37 | [9 empty] | 0
Schedule 16 | 38 | [9 empty] | 0
Schedule 16 | 39 | [9 empty] | 0
Schedule 16 | 40 | [9 empty] | 0
Schedule 16 | 41 | [9 empty] | 0
Schedule 16 | 41A | [9 empty] | 0
Schedule 16 | 41B | [9 empty] | 0
Schedule 16 | 42 | [9 empty] | 0
Schedule 16 | 42A | [9 empty] | 0
Schedule 16 | 43 | [9 empty] | 0
Schedule 16 | 44 | [9 empty] | 0
Schedule 16 | 45 | [9 empty] | 0
Schedule 16 | 46 | [9 empty] | 0
Schedule 16 | 47 | [9 empty] | 0
Schedule 16 | 48 | [9 empty] | 0
Schedule 16 | 49 | [9 empty] | 0
Schedule 16 | 50 | [9 empty] | 0
Schedule 16 | 51 | [9 empty] | 0
Schedule 16 | 52 | [9 empty] | 0
Schedule 16 | 52A | [9 empty] | 0
Schedule 16 | 53 | [9 empty] | 0
Schedule 16 | 54 | [9 empty] | 0
Schedule 16 | 55 | [9 empty] | 0
Schedule 16 | 56 | [9 empty] | 0
Schedule 16 | 57 | [9 empty] | 0
Schedule 16 | 58 | [9 empty] | 0
Schedule 16 | 59 | [9 empty] | 0
Schedule 16 | 60 | [9 empty] | 0
Schedule 16 | 61 | [9 empty] | 0
Schedule 16 | 62 | [9 empty] | 0
Schedule 16 | 63 | [9 empty] | 0
Schedule 16 | 64 | [9 empty] | 0
Schedule 16 | 65 | [9 empty] | 0
Schedule 16 | 66 | [9 empty] | 0
Schedule 16 | 67 | [9 empty] | 0
Schedule 16 | 68 | [9 empty] | 0
Schedule 16 | 69 | [9 empty] | 0
Schedule 16 | 70 | [9 empty] | 0
Schedule 16 | 71 | [9 empty] | 0
Schedule 16 | 72 | [9 empty] | 0
Schedule 16 | 72A | [9 empty] | 0
Schedule 16 | 73 | [9 empty] | 0
Schedule 16 | 74 | [9 empty] | 0
Schedule 16 | 75 | [9 empty] | 0
Schedule 16 | 76 | [9 empty] | 0
Schedule 16 | 77 | [9 empty] | 0
Schedule 16 | 78 | [9 empty] | 0
Schedule 16 | 79 | [9 empty] | 0
Schedule 16 | 80 | [9 empty] | 0
Schedule 16 | 81 | [9 empty] | 0
Schedule 16 | 82 | [9 empty] | 0
Schedule 16 | 83 | [9 empty] | 0
Schedule 16 | 84 | [9 empty] | 0
Schedule 16 | 85 | [9 empty] | 0
Schedule 16 | 86 | [9 empty] | 0
Schedule 16 | 87 | [9 empty] | 0
Schedule 16 | 88 | [9 empty] | 0
Schedule 16 | 89 | [9 empty] | 0
Schedule 16 | 90 | [9 empty] | 0
Schedule 16 | 91 | [9 empty] | 0
Schedule 16 | 92 | [9 empty] | 0
Schedule 16 | 92A | [9 empty] | 0
Schedule 16 | 92B | [9 empty] | 0
Schedule 16 | 92C | [9 empty] | 0
Schedule 16 | 93 | [9 empty] | 0
Schedule 16 | 94 | [9 empty] | 0
Schedule 16 | 94A | [9 empty] | 0
Schedule 16 | 94B | [5 empty] | YES |  |  |  | 1
Schedule 16 | 95 | [9 empty] | 0
Schedule 16 | 96 | [9 empty] | 0
Schedule 16 | 97 | [9 empty] | 0
Schedule 16 | 98 | [9 empty] | 0
Schedule 16 | 99 | [9 empty] | 0
Schedule 16 | 100 | [9 empty] | 0
Schedule 16 | 101 | [9 empty] | 0
Schedule 16 | 102 | [9 empty] | 0
Schedule 16 | 102A | [9 empty] | 0
Schedule 16 | 102B | [9 empty] | 0
Schedule 16 | 103 | [9 empty] | 0
Schedule 16 | 104 | [9 empty] | 0
Schedule 16 | 105 | [9 empty] | 0
Schedule 16 | 106 | [9 empty] | 0
Schedule 16 | 107 | [9 empty] | 0
Schedule 16 | 108 | [9 empty] | 0
Schedule 16 | 108A | [9 empty] | 0
Schedule 16 | 109 | [9 empty] | 0
Schedule 16 | 110 | [9 empty] | 0
Schedule 16 | 111 | [9 empty] | 0
Schedule 16 | 112 | [9 empty] | 0
Schedule 16 | 112A | [9 empty] | 0
Schedule 16 | 113 | [9 empty] | 0
Schedule 16 | 113A | [9 empty] | 0
Schedule 16 | 113B | [9 empty] | 0
Schedule 16 | 113C | [9 empty] | 0
Schedule 16 | 113D | [9 empty] | 0
Schedule 16 | 113E | [9 empty] | 0
Schedule 16 | 114 | [9 empty] | 0
Schedule 16 | 115 | [9 empty] | 0
Schedule 16 | 116 | [9 empty] | 0
Schedule 16 | 117 | [9 empty] | 0
Schedule 16 | 118 | [9 empty] | 0
Schedule 16 | 119 | [9 empty] | 0
Schedule 16 | 120 | [9 empty] | 0
Schedule 16 | 121 | [9 empty] | 0
Schedule 16 | 122 | [9 empty] | 0
Schedule 16 | 123 | [9 empty] | 0
Schedule 16 | 124 | [9 empty] | 0
Schedule 16 | 125 | [9 empty] | 0
Schedule 16 | 126 | [9 empty] | 0
Schedule 16 | 127 | [9 empty] | 0
Schedule 16 | 127A | [9 empty] | 0
Schedule 16 | 128 | YES | [8 empty] | 1
Schedule 16 | 129 | [9 empty] | 0
Schedule 16 | 130 | [9 empty] | 0
Schedule 16 | 131 | [9 empty] | 0
Schedule 16 | 132 | [9 empty] | 0
Schedule 16 | 132A | [9 empty] | 0
Schedule 16 | 132B | [9 empty] | 0
Schedule 16 | 132C | [9 empty] | 0
Schedule 16 | 132D | [9 empty] | 0
Schedule 16 | 133 | [9 empty] | 0
Schedule 16 | 134 | [9 empty] | 0
Schedule 16 | 135 | [9 empty] | 0
Schedule 16 | 135A | [9 empty] | 0 | MHHS CP seeks to remove the last column containing applicable Measurement Class
Schedule 16 | 135B | [9 empty] | 0
Schedule 16 | 136 | [9 empty] | 0
Schedule 16 | 137 | [9 empty] | 0
Schedule 16 | 138 | [9 empty] | 0
Schedule 16 | 139 |  |  |  |  | YES |  |  | YES |  | 2
Schedule 16 | 140 |  |  |  |  | YES |  |  | YES |  | 2
Schedule 16 | 140A | [9 empty] | 0
Schedule 16 | 140B | [9 empty] | 0
Schedule 16 | 140C | [9 empty] | 0
Schedule 16 | 140D | [9 empty] | 0
Schedule 16 | 140E | [9 empty] | 0
Schedule 16 | 141 | [9 empty] | 0
Schedule 16 | 142 | [9 empty] | 0
Schedule 16 | 143 | [9 empty] | 0
Schedule 16 | 144 | [9 empty] | 0
Schedule 16 | 145 | [9 empty] | 0
Schedule 16 | 146 | [9 empty] | 0
Schedule 16 | 147 | [9 empty] | 0
Schedule 16 | 148 | [9 empty] | 0
Schedule 16 | 149 | [9 empty] | 0
Schedule 16 | 150 | [9 empty] | 0
Schedule 16 | 151 | [9 empty] | 0
Schedule 16 | 152 | [9 empty] | 0
Schedule 16 | 153 | [6 empty] | YES |  |  | 1
Schedule 16 | 154 | [9 empty] | 0
Schedule 16 | 155 | [9 empty] | 0
Schedule 16 | 156 | [9 empty] | 0
Schedule 16 | 157 | [9 empty] | 0
Schedule 16 | 158 | [9 empty] | 0
Schedule 16 | 159 | [9 empty] | 0
Schedule 16 | 160 | [9 empty] | 0
Schedule 16 | 161 | [9 empty] | 0
Schedule 16 | 162 | [9 empty] | 0
Schedule 16 | 163 | [9 empty] | 0
Schedule 16 | 164 | [9 empty] | 0
Schedule 16 | 165 | [9 empty] | 0
Schedule 16 | 166 | [9 empty] | 0
Schedule 16 | 167 | [9 empty] | 0
Schedule 16 | 168 | [9 empty] | 0
Schedule 16 | 169 | [9 empty] | 0
Schedule 16 | 170 | [9 empty] | 0
Schedule 16 | 171 | [9 empty] | 0
Schedule 16 | 172 | [9 empty] | 0
Schedule 16 | 173 | [9 empty] | 0
Schedule 16 | 173A | [9 empty] | 0 | DCP 439 Introduces new Paragraph 173A
Schedule 16 | 174 | [9 empty] | 0
Schedule 16 | 175 | [9 empty] | 0
Schedule 16 | 176 | [9 empty] | 0
Schedule 16 | 177 | [9 empty] | 0
Schedule 16 | 178 | [9 empty] | 0
Schedule 16 | 179 | [9 empty] | 0
Schedule 16 | 180 | [9 empty] | 0
Schedule 16 | 181 | [9 empty] | 0
Schedule 16 | 182 | [9 empty] | 0
Schedule 16 | 183 | [9 empty] | 0
Schedule 16 | 184 | [9 empty] | 0
Schedule 16 | Glossary | [9 empty] | 0
0
Schedule 17 | Introduction | [9 empty] | 0
Schedule 17 | 1 | [9 empty] | 0
Schedule 17 | 1.1 | [9 empty] | 0
Schedule 17 | 1.2 | [9 empty] | 0
Schedule 17 | 1.3 | [9 empty] | 0 | Model reference number and date
Schedule 17 | 1.3A | [9 empty] | 0
Schedule 17 | 1.4 | [9 empty] | 0
Schedule 17 | 1.5 | [9 empty] | 0
Schedule 17 | 1.6 | [9 empty] | 0
Schedule 17 | 1.7 | [9 empty] | 0
Schedule 17 | 1.8 | [9 empty] | 0
Schedule 17 | 1.9 | [9 empty] | 0
Schedule 17 | 2 | [9 empty] | 0
Schedule 17 | 2.1 | [9 empty] | 0
Schedule 17 | 2.2 | [9 empty] | 0
Schedule 17 | 2.3 | [9 empty] | 0
Schedule 17 | 2.4 | [9 empty] | 0
Schedule 17 | 2.5 | [9 empty] | 0
Schedule 17 | 2.6 | [9 empty] | 0
Schedule 17 | 2.7 | [8 empty] | YES | 1
Schedule 17 | 2.8 | [9 empty] | 0
Schedule 17 | 2.9 | [9 empty] | 0
Schedule 17 | 2.1 | [9 empty] | 0
Schedule 17 | 2.11 | [9 empty] | 0
Schedule 17 | 2.12 | [9 empty] | 0
Schedule 17 | 2.13 | [9 empty] | 0
Schedule 17 | 2.14 | [9 empty] | 0
Schedule 17 | 2.15 | [9 empty] | 0
Schedule 17 | 2.16 | [9 empty] | 0
Schedule 17 | 2.17 | [9 empty] | 0
Schedule 17 | 2.18 | [9 empty] | 0
Schedule 17 | 2.19 | [9 empty] | 0
Schedule 17 | 3 | [9 empty] | 0
Schedule 17 | 3.1 | [9 empty] | 0
Schedule 17 | 3.2 | [9 empty] | 0
Schedule 17 | 3.3 | [9 empty] | 0
Schedule 17 | 3.4 | [9 empty] | 0
Schedule 17 | 3.5 | [9 empty] | 0
Schedule 17 | 3.6 | [9 empty] | 0
Schedule 17 | 3.7 | [9 empty] | 0
Schedule 17 | 4 | [9 empty] | 0
Schedule 17 | 4.1 | [9 empty] | 0
Schedule 17 | 5 | [9 empty] | 0
Schedule 17 | 5.1 | [9 empty] | 0
Schedule 17 | 6 | [9 empty] | 0
Schedule 17 | 6.1 | [9 empty] | 0
Schedule 17 | 6.2 | [8 empty] | YES | 1
Schedule 17 | 6.3 | [8 empty] | YES | 1
Schedule 17 | 7 | [9 empty] | 0
Schedule 17 | 7.1 | [9 empty] | 0
Schedule 17 | 8 | [9 empty] | 0
Schedule 17 | 8.1 | [9 empty] | 0
Schedule 17 | 8.2 | [9 empty] | 0
Schedule 17 | 8.3 | [9 empty] | 0
Schedule 17 | 8.4 | [9 empty] | 0
Schedule 17 | 9 | [9 empty] | 0
Schedule 17 | 9.1 | [9 empty] | 0
Schedule 17 | 9.2 | [9 empty] | 0
Schedule 17 | 9.3 | [9 empty] | 0
Schedule 17 | 10 | [9 empty] | 0
Schedule 17 | 10.1 | [9 empty] | 0
Schedule 17 | 10.2 | [9 empty] | 0
Schedule 17 | 10.3 | [9 empty] | 0
Schedule 17 | 10.4 | [9 empty] | 0
Schedule 17 | 11 | [9 empty] | 0
Schedule 17 | 11.1 | [9 empty] | 0
Schedule 17 | 12 | [9 empty] | 0
Schedule 17 | 12.1 | [9 empty] | 0
Schedule 17 | 12.2 | [9 empty] | 0
Schedule 17 | 12.3 | [9 empty] | 0
Schedule 17 | 13 | [9 empty] | 0
Schedule 17 | 13.1 | [9 empty] | 0
Schedule 17 | 13.2 | [9 empty] | 0
Schedule 17 | 13.3 | [9 empty] | 0
Schedule 17 | 13.4 | [9 empty] | 0
Schedule 17 | 14 | [9 empty] | 0
Schedule 17 | 14.1 | [9 empty] | 0
Schedule 17 | 14.2 | [9 empty] | 0
Schedule 17 | 14.3 | [9 empty] | 0
Schedule 17 | 14.4 | [9 empty] | 0
Schedule 17 | 14.5 | [9 empty] | 0
Schedule 17 | 15 | [9 empty] | 0
Schedule 17 | 15.1 | [9 empty] | 0
Schedule 17 | 15.2 | [9 empty] | 0
Schedule 17 | 15.3 | [9 empty] | 0
Schedule 17 | 15.4 | [9 empty] | 0
Schedule 17 | 15.5 | [9 empty] | 0
Schedule 17 | 15.6 | [9 empty] | 0
Schedule 17 | 15.7 | [9 empty] | 0
Schedule 17 | 15.8 | [9 empty] | 0
Schedule 17 | 15.9 | [9 empty] | 0
Schedule 17 | 15.1 | [9 empty] | 0
Schedule 17 | 15.11 | [9 empty] | 0
Schedule 17 | 15.12 | [9 empty] | 0
Schedule 17 | 15.15 | [9 empty] | 0
Schedule 17 | 16 | [9 empty] | 0
Schedule 17 | 16.1 | [9 empty] | 0
Schedule 17 | 16.2 | [9 empty] | 0
Schedule 17 | 16.3 | [9 empty] | 0
Schedule 17 | 16.4 | [9 empty] | 0
Schedule 17 | 16.5 | [9 empty] | 0
Schedule 17 | 16.6 | [9 empty] | 0
Schedule 17 | 16.7 | [9 empty] | 0
Schedule 17 | 16.8 | [9 empty] | 0
Schedule 17 | 16.9 | [9 empty] | 0
Schedule 17 | 16.1 | [9 empty] | 0
Schedule 17 | 17 | [9 empty] | 0
Schedule 17 | 17.1 | [9 empty] | 0
Schedule 17 | 17.2 | [9 empty] | 0
Schedule 17 | 17.3 | [9 empty] | 0
Schedule 17 | 18 | [9 empty] | 0
Schedule 17 | 18.1 | [9 empty] | 0
Schedule 17 | 18.2 | [9 empty] | 0
Schedule 17 | 18.3 | [9 empty] | 0
Schedule 17 | 18.4 | [9 empty] | 0
Schedule 17 | 18.5 | [9 empty] | 0
Schedule 17 | 18.6 | [9 empty] | 0
Schedule 17 | 18.7 | [9 empty] | 0
Schedule 17 | 18.8 | [9 empty] | 0
Schedule 17 | 18.9 | [9 empty] | 0
Schedule 17 | 18.1 | [9 empty] | 0
Schedule 17 | 18.11 | [9 empty] | 0
Schedule 17 | 18.12 | [9 empty] | 0
Schedule 17 | 18.13 | [9 empty] | 0
Schedule 17 | 18.14 | [9 empty] | 0
Schedule 17 | 18.15 | [9 empty] | 0
Schedule 17 | 18.16 | [9 empty] | 0
Schedule 17 | 18.17 | [9 empty] | 0
Schedule 17 | 18.18 | [9 empty] | 0
Schedule 17 | 18.19 | [9 empty] | 0
Schedule 17 | 18.2 | [9 empty] | 0
Schedule 17 | 18.21 | [9 empty] | 0
Schedule 17 | 19 | [9 empty] | 0
Schedule 17 | 19.1 | [9 empty] | 0
Schedule 17 | 19.2 | [9 empty] | 0
Schedule 17 | 19.3 | [9 empty] | 0
Schedule 17 | 19.4 | [9 empty] | 0
Schedule 17 | 19.5 | [9 empty] | 0
Schedule 17 | 19.6 | [9 empty] | 0
Schedule 17 | 19.7 | [9 empty] | 0
Schedule 17 | 19.8 | [9 empty] | 0
Schedule 17 | 19.9 | [9 empty] | 0
Schedule 17 | 19.1 | [9 empty] | 0
Schedule 17 | 19.11 | [9 empty] | 0
Schedule 17 | 20 | [9 empty] | 0
Schedule 17 | 20.1 | [9 empty] | 0
Schedule 17 | 20.2 | [9 empty] | 0
Schedule 17 | 20.3 | [9 empty] | 0
Schedule 17 | 20.4 | [9 empty] | 0
Schedule 17 | 20.5 | [9 empty] | 0
Schedule 17 | 20.6 | [6 empty] | YES |  |  | 1
Schedule 17 | 20.7 | [6 empty] | YES |  |  | 1
Schedule 17 | 20.8 | [9 empty] | 0
Schedule 17 | 20.9 | [6 empty] | YES |  |  | 1
Schedule 17 | 21 | [9 empty] | 0
Schedule 17 | 21.1 | [9 empty] | 0
Schedule 17 | 21.2 | [9 empty] | 0
Schedule 17 | 22 | [9 empty] | 0
Schedule 17 | 22.1 | [9 empty] | 0
Schedule 17 | 22.2 | [9 empty] | 0
Schedule 17 | 22.3 | [9 empty] | 0
Schedule 17 | 22.4 | [9 empty] | 0
Schedule 17 | 23 | [9 empty] | 0
Schedule 17 | 23.1 | [9 empty] | 0
Schedule 17 | 23.2 | [9 empty] | 0
Schedule 17 | 23.3 | [9 empty] | 0
Schedule 17 | 23.4 | [9 empty] | 0
Schedule 17 | 23.5 | [9 empty] | 0
Schedule 17 | 24 | [9 empty] | 0
Schedule 17 | 24.1 | [9 empty] | 0
Schedule 17 | 24.2 | [9 empty] | 0
Schedule 17 | 24.3 | [9 empty] | 0
Schedule 17 | 24.4 | [9 empty] | 0
Schedule 17 | 24.5 | [9 empty] | 0
Schedule 17 | 24.6 | [9 empty] | 0
Schedule 17 | 24.7 | [9 empty] | 0
Schedule 17 | 24.8 | [9 empty] | 0
Schedule 17 | 24.9 | [9 empty] | 0
Schedule 17 | 25 | [9 empty] | 0
Schedule 17 | 25.1 | [9 empty] | 0
Schedule 17 | 25.2 | [9 empty] | 0
Schedule 17 | 25.3 | [9 empty] | 0
Schedule 17 | 25.4 | [9 empty] | 0
Schedule 17 | 25.5 | [9 empty] | 0
Schedule 17 | 25.6 | [9 empty] | 0
Schedule 17 | 25.7 | [9 empty] | 0
Schedule 17 | 25.8 | [9 empty] | 0
Schedule 17 | 25.9 | [9 empty] | 0
Schedule 17 | 25.1 | [9 empty] | 0
Schedule 17 | 25.11 | [9 empty] | 0
Schedule 17 | 25.12 | [9 empty] | 0
Schedule 17 | 25.13 | [9 empty] | 0
Schedule 17 | 25.14 | [9 empty] | 0
Schedule 17 | 25.15 | [9 empty] | 0
Schedule 17 | 25.16 | [9 empty] | 0
Schedule 17 | 25.17 | [9 empty] | 0
Schedule 17 | 25.18 | [9 empty] | 0
Schedule 17 | 25.19 | [9 empty] | 0
Schedule 17 | 26 | [9 empty] | 0
Schedule 17 | 26.1 | [9 empty] | 0
Schedule 17 | 26.2 | [9 empty] | 0
Schedule 17 | 26.3 | [9 empty] | 0
Schedule 17 | 26.4 | [9 empty] | 0
Schedule 17 | 26.5 | [9 empty] | 0
Schedule 17 | 26.6 | [9 empty] | 0
Schedule 17 | 26.7 | [9 empty] | 0
Schedule 17 | 26.8 | [9 empty] | 0
Schedule 17 | 26.9 | [9 empty] | 0
Schedule 17 | 26.1 | [9 empty] | 0
Schedule 17 | 26.11 | [9 empty] | 0
Schedule 17 | 27 | [9 empty] | 0
Schedule 17 | 27.1 | [9 empty] | 0
Schedule 17 | 27.2 | [9 empty] | 0
Schedule 17 | 27.3 | [9 empty] | 0
Schedule 17 | 27.4 | [9 empty] | 0
Schedule 17 | 28 | [9 empty] | 0
Schedule 17 | 28.1 | [9 empty] | 0
Schedule 17 | 28.2 | [9 empty] | 0
Schedule 17 | 29 | [9 empty] | 0
Schedule 17 | 29.1 | [9 empty] | 0
Schedule 17 | 29.2 | [9 empty] | 0
Schedule 17 | 29.3 | [9 empty] | 0
Schedule 17 | 29.4 | [9 empty] | 0
Schedule 17 | 30 | [9 empty] | 0
Schedule 17 | 30.1 | [9 empty] | 0
Schedule 17 | 30.2 | [9 empty] | 0
Schedule 17 | 30.3 | [9 empty] | 0
Schedule 17 | 30.4 | [9 empty] | 0
Schedule 17 | 30.5 | [9 empty] | 0
Schedule 17 | 30.6 | [9 empty] | 0
Schedule 17 | 30.7 | [9 empty] | 0
Schedule 17 | 30.8 | [9 empty] | 0
Schedule 17 | 30.9 | [9 empty] | 0
Schedule 17 | 30.1 | [9 empty] | 0
Schedule 17 | 30.11 | [9 empty] | 0
Schedule 17 | 31 | [9 empty] | 0 | DCP 439 Introduces new Paragraph 31
Schedule 17 | 31.1 | [9 empty] | 0 | DCP 439 Introduces new Paragraph 31.1
Schedule 17: Annex 1 | 1 | [9 empty] | 0
Schedule 17: Annex 1 | 2 | [9 empty] | 0
Schedule 17: Annex 1 | 2.1 | [9 empty] | 0
Schedule 17: Annex 1 | 2.2 | [9 empty] | 0
Schedule 17: Annex 1 | 2.3 | [9 empty] | 0
Schedule 17: Annex 1 | 2.4 | [9 empty] | 0
Schedule 17: Annex 1 | 2.5 | [9 empty] | 0
Schedule 17: Annex 1 | 3 | [9 empty] | 0
Schedule 17: Annex 1 | Definitions | [9 empty] | 0
Schedule 17: Annex 1 | 4 | [9 empty] | 0
Schedule 17: Annex 1 | 4.1 | [9 empty] | 0
Schedule 17: Annex 1 | 4.2 | [9 empty] | 0
Schedule 17: Annex 1 | 4.3 | [9 empty] | 0
Schedule 17: Annex 1 | 4.4 | [9 empty] | 0
Schedule 17: Annex 1 | 4.5 | [9 empty] | 0
Schedule 17: Annex 1 | 4.6 | [9 empty] | 0
Schedule 17: Annex 1 | 4.7 | [9 empty] | 0
Schedule 17: Annex 1 | 4.8 | [9 empty] | 0
Schedule 17: Annex 1 | 4.9 | [9 empty] | 0
Schedule 17: Annex 1 | 4.1 | [9 empty] | 0
Schedule 17: Annex 1 | 5 | [9 empty] | 0
Schedule 17: Annex 1 | 5.1 | [9 empty] | 0
Schedule 17: Annex 1 | 5.2 | [9 empty] | 0
Schedule 17: Annex 1 | 5.3 | [9 empty] | 0
Schedule 17: Annex 1 | 5.4 | [9 empty] | 0
Schedule 17: Annex 1 | 5.5 | [9 empty] | 0
Schedule 17: Annex 1 | 5.6 | [9 empty] | 0
Schedule 17: Annex 1 | 5.7 | [9 empty] | 0
Schedule 17: Annex 1 | 5.8 | [9 empty] | 0
Schedule 17: Annex 1 | 5.9 | [9 empty] | 0
Schedule 17: Annex 1 | 5.1 | [9 empty] | 0
Schedule 17: Annex 1 | 5.11 | [9 empty] | 0
Schedule 17: Annex 1 | 5.12 | [9 empty] | 0
Schedule 17: Annex 1 | 5.13 | [9 empty] | 0
Schedule 17: Annex 1 | 5.14 | [9 empty] | 0
Schedule 17: Annex 1 | 5.15 | [9 empty] | 0
Schedule 17: Annex 1 | 5.16 | [9 empty] | 0
Schedule 17: Annex 1 | 5.17 | [9 empty] | 0
Schedule 17: Annex 1 | 5.18 | [9 empty] | 0
Schedule 17: Annex 1 | 5.19 | [9 empty] | 0
Schedule 17: Annex 1 | 5.2 | [9 empty] | 0
Schedule 17: Annex 1 | 5.21 | [9 empty] | 0
Schedule 17: Annex 1 | 5.22 | [9 empty] | 0
Schedule 17: Annex 1 | 5.23 | [9 empty] | 0
Schedule 17: Annex 1 | 5.24 | [9 empty] | 0
Schedule 17: Annex 1 | 5.25 | [9 empty] | 0
Schedule 17: Annex 1 | 5.26 | [9 empty] | 0
Schedule 17: Annex 1 | 5.27 | [9 empty] | 0
Schedule 17: Annex 1 | 5.28 | [9 empty] | 0
Schedule 17: Annex 1 | 5.29 | [9 empty] | 0
Schedule 17: Annex 1 | 5.3 | [9 empty] | 0
Schedule 17: Annex 1 | 5.31 | [9 empty] | 0
Schedule 17: Annex 1 | 5.32 | [9 empty] | 0
Schedule 17: Annex 1 | 5.33 | [9 empty] | 0
Schedule 17: Annex 1 | 5.34 | [9 empty] | 0
Schedule 17: Annex 1 | 5.35 | [9 empty] | 0
Schedule 17: Annex 1 | 5.36 | [9 empty] | 0
Schedule 17: Annex 1 | 5.37 | [9 empty] | 0
Schedule 17: Annex 1 | 5.38 | [9 empty] | 0
Schedule 17: Annex 1 | 5.39 | [9 empty] | 0
Schedule 17: Annex 1 | 5.4 | [9 empty] | 0
Schedule 17: Annex 1 | 5.41 | [9 empty] | 0
Schedule 17: Annex 1 | 5.42 | [9 empty] | 0
Schedule 17: Annex 1 | 5.43 | [9 empty] | 0
Schedule 17: Annex 1 | 5.44 | [9 empty] | 0
Schedule 17: Annex 1 | 5.45 | [9 empty] | 0
Schedule 17: Annex 1 | 6 | [9 empty] | 0
Schedule 17: Annex 1 | 6.1 | [9 empty] | 0
Schedule 17: Annex 1 | 6.2 | [9 empty] | 0
Schedule 17: Annex 1 | 6.3 | [8 empty] | YES | 1
Schedule 17: Annex 1 | 6.4 | [9 empty] | 0
Schedule 17: Annex 1 | 6.5 | [9 empty] | 0
Schedule 17: Annex 1 | 6.6 | [9 empty] | 0
Schedule 17: Annex 1 | 6.7 | [9 empty] | 0
Schedule 17: Annex 1 | 6.8 | [9 empty] | 0
Schedule 17: Annex 1 | 7 | [9 empty] | 0
Schedule 17: Annex 1 | 7.1 | [9 empty] | 0
Schedule 17: Annex 1 | 7.2 | [9 empty] | 0
Schedule 17: Annex 1 | 7.3 | [9 empty] | 0
Schedule 17: Annex 1 | 7.4 | [9 empty] | 0
Schedule 17: Annex 1 | 7.5 | [9 empty] | 0
Schedule 17: Annex 1 | 7.6 | [9 empty] | 0
Schedule 17: Annex 1 | 7.7 | [9 empty] | 0
Schedule 17: Annex 1 | 7.8 | [9 empty] | 0
Schedule 17: Annex 1 | 8 | [9 empty] | 0
Schedule 17: Annex 1 | 8.1 | [9 empty] | 0
Schedule 17: Annex 1 | 8.2 | [9 empty] | 0
Schedule 17: Annex 1 | 8.3 | [9 empty] | 0
Schedule 17: Annex 1 | 8.4 | [9 empty] | 0
Schedule 17: Annex 1 | 9 | [9 empty] | 0
Schedule 17: Annex 1 | 9.1 | [9 empty] | 0
Schedule 17: Annex 1 | 9.2 | [9 empty] | 0
Schedule 17: Annex 1 | 9.3 | [9 empty] | 0
Schedule 17: Annex 1 | 9.4 | [9 empty] | 0
Schedule 17: Annex 1 | 9.5 | [9 empty] | 0
Schedule 17: Annex 1 | 9.6 | [9 empty] | 0
Schedule 17: Annex 1 | 9.7 | [9 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [9 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [9 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [9 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [9 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [9 empty] | 0
0
Schedule 18 | Introduction | [9 empty] | 0
Schedule 18 | 1 | [9 empty] | 0
Schedule 18 | 1.1 | [9 empty] | 0
Schedule 18 | 1.2 | [9 empty] | 0
Schedule 18 | 1.3 | [9 empty] | 0 | Model reference number and date
Schedule 18 | 1.3A | [9 empty] | 0
Schedule 18 | 1.4 | [9 empty] | 0
Schedule 18 | 1.5 | [9 empty] | 0
Schedule 18 | 1.6 | [9 empty] | 0
Schedule 18 | 1.7 | [9 empty] | 0
Schedule 18 | 1.8 | [9 empty] | 0
Schedule 18 | 1.9 | [9 empty] | 0
Schedule 18 | 2 | [9 empty] | 0
Schedule 18 | 2.1 | [9 empty] | 0
Schedule 18 | 2.2 | [9 empty] | 0
Schedule 18 | 2.3 | [9 empty] | 0
Schedule 18 | 2.4 | [9 empty] | 0
Schedule 18 | 2.5 | [9 empty] | 0
Schedule 18 | 2.6 | [9 empty] | 0
Schedule 18 | 2.7 | [9 empty] | 0
Schedule 18 | 2.8 | [9 empty] | 0
Schedule 18 | 2.9 | [9 empty] | 0
Schedule 18 | 2.1 | [9 empty] | 0
Schedule 18 | 2.11 | [9 empty] | 0
Schedule 18 | 2.12 | [9 empty] | 0
Schedule 18 | 2.13 | [9 empty] | 0
Schedule 18 | 2.14 | [9 empty] | 0
Schedule 18 | 2.15 | [9 empty] | 0
Schedule 18 | 2.16 | [9 empty] | 0
Schedule 18 | 2.17 | [9 empty] | 0
Schedule 18 | 2.18 | [9 empty] | 0
Schedule 18 | 2.19 | [9 empty] | 0
Schedule 18 | 2.2 | [9 empty] | 0
Schedule 18 | 2.21 | [9 empty] | 0
Schedule 18 | 2.22 | [9 empty] | 0
Schedule 18 | 2.23 | [9 empty] | 0
Schedule 18 | 2.24 | [9 empty] | 0
Schedule 18 | 2.25 | [9 empty] | 0
Schedule 18 | 2.26 | [9 empty] | 0
Schedule 18 | 2.27 | [9 empty] | 0
Schedule 18 | 2.28 | [9 empty] | 0
Schedule 18 | 2.29 | [9 empty] | 0
Schedule 18 | 2.3 | [9 empty] | 0
Schedule 18 | 3 | [9 empty] | 0
Schedule 18 | 3.1 | [9 empty] | 0
Schedule 18 | 3.2 | [9 empty] | 0
Schedule 18 | 3.3 | [9 empty] | 0
Schedule 18 | 3.4 | [9 empty] | 0
Schedule 18 | 3.5 | [9 empty] | 0
Schedule 18 | 3.6 | [9 empty] | 0
Schedule 18 | 3.7 | [9 empty] | 0
Schedule 18 | 4 | [9 empty] | 0
Schedule 18 | 4.1 | [9 empty] | 0
Schedule 18 | 5 | [9 empty] | 0
Schedule 18 | 5.1 | [9 empty] | 0
Schedule 18 | 6 | [9 empty] | 0
Schedule 18 | 6.1 | [9 empty] | 0
Schedule 18 | 6.2 | [9 empty] | 0
Schedule 18 | 6.3 | [9 empty] | 0
Schedule 18 | 6.4 | [9 empty] | 0
Schedule 18 | 6.5 | [9 empty] | 0
Schedule 18 | 7 | [9 empty] | 0
Schedule 18 | 7.1 | [9 empty] | 0
Schedule 18 | 8 | [9 empty] | 0
Schedule 18 | 8.1 | [9 empty] | 0
Schedule 18 | 8.2 | [9 empty] | 0
Schedule 18 | 8.3 | [9 empty] | 0
Schedule 18 | 8.4 | [9 empty] | 0
Schedule 18 | 9 | [9 empty] | 0
Schedule 18 | 9.1 | [9 empty] | 0
Schedule 18 | 9.2 | [9 empty] | 0
Schedule 18 | 10 | [9 empty] | 0
Schedule 18 | 10.1 | [9 empty] | 0
Schedule 18 | 10.2 | [9 empty] | 0
Schedule 18 | 10.3 | [9 empty] | 0
Schedule 18 | 10.4 | [9 empty] | 0
Schedule 18 | 10.5 | [9 empty] | 0
Schedule 18 | 11 | [9 empty] | 0
Schedule 18 | 11.1 | [9 empty] | 0
Schedule 18 | 12 | [9 empty] | 0
Schedule 18 | 12.1 | [9 empty] | 0
Schedule 18 | 12.2 | [9 empty] | 0
Schedule 18 | 12.3 | [9 empty] | 0
Schedule 18 | 12.4 | [9 empty] | 0
Schedule 18 | 12.5 | [9 empty] | 0
Schedule 18 | 12.6 | [9 empty] | 0
Schedule 18 | 13 | [9 empty] | 0
Schedule 18 | 13.1 | [9 empty] | 0
Schedule 18 | 13.2 | [9 empty] | 0
Schedule 18 | 13.3 | [9 empty] | 0
Schedule 18 | 13.4 | [9 empty] | 0
Schedule 18 | 14 | [9 empty] | 0
Schedule 18 | 14.1 | [9 empty] | 0
Schedule 18 | 14.2 | [9 empty] | 0
Schedule 18 | 14.3 | [9 empty] | 0
Schedule 18 | 14.4 | [9 empty] | 0
Schedule 18 | 14.5 | [9 empty] | 0
Schedule 18 | 15 | [9 empty] | 0
Schedule 18 | 15.1 | [9 empty] | 0
Schedule 18 | 15.2 | [9 empty] | 0
Schedule 18 | 15.3 | [9 empty] | 0
Schedule 18 | 15.4 | [9 empty] | 0
Schedule 18 | 15.5 | [9 empty] | 0
Schedule 18 | 15.6 | [9 empty] | 0
Schedule 18 | 15.7 | [9 empty] | 0
Schedule 18 | 15.8 | [9 empty] | 0
Schedule 18 | 15.9 | [9 empty] | 0
Schedule 18 | 15.1 | [9 empty] | 0
Schedule 18 | 15.11 | [9 empty] | 0
Schedule 18 | 15.12 | [9 empty] | 0
Schedule 18 | 15.15 | [9 empty] | 0
Schedule 18 | 16 | [9 empty] | 0
Schedule 18 | 16.1 | [9 empty] | 0
Schedule 18 | 16.2 | [9 empty] | 0
Schedule 18 | 16.3 | [9 empty] | 0
Schedule 18 | 16.4 | [9 empty] | 0
Schedule 18 | 16.5 | [9 empty] | 0
Schedule 18 | 16.6 | [9 empty] | 0
Schedule 18 | 16.7 | [9 empty] | 0
Schedule 18 | 16.8 | [9 empty] | 0
Schedule 18 | 16.9 | [9 empty] | 0
Schedule 18 | 16.1 | [9 empty] | 0
Schedule 18 | 17 | [9 empty] | 0
Schedule 18 | 17.1 | [9 empty] | 0
Schedule 18 | 17.2 | [9 empty] | 0
Schedule 18 | 17.3 | [9 empty] | 0
Schedule 18 | 18 | [9 empty] | 0
Schedule 18 | 18.1 | [9 empty] | 0
Schedule 18 | 18.2 | [9 empty] | 0
Schedule 18 | 18.3 | [9 empty] | 0
Schedule 18 | 18.4 | [9 empty] | 0
Schedule 18 | 18.5 | [9 empty] | 0
Schedule 18 | 18.6 | [9 empty] | 0
Schedule 18 | 18.7 | [9 empty] | 0
Schedule 18 | 18.8 | [9 empty] | 0
Schedule 18 | 18.9 | [9 empty] | 0
Schedule 18 | 18.1 | [9 empty] | 0
Schedule 18 | 18.11 | [9 empty] | 0
Schedule 18 | 18.12 | [9 empty] | 0
Schedule 18 | 18.13 | [9 empty] | 0
Schedule 18 | 18.14 | [9 empty] | 0
Schedule 18 | 18.15 | [9 empty] | 0
Schedule 18 | 18.16 | [9 empty] | 0
Schedule 18 | 18.17 | [9 empty] | 0
Schedule 18 | 18.18 | [9 empty] | 0
Schedule 18 | 18.19 | [9 empty] | 0
Schedule 18 | 18.2 | [9 empty] | 0
Schedule 18 | 18.21 | [9 empty] | 0
Schedule 18 | 19 | [9 empty] | 0
Schedule 18 | 19.1 | [9 empty] | 0
Schedule 18 | 19.2 | [9 empty] | 0
Schedule 18 | 19.3 | [9 empty] | 0
Schedule 18 | 19.4 | [9 empty] | 0
Schedule 18 | 19.5 | [9 empty] | 0
Schedule 18 | 19.6 | [9 empty] | 0
Schedule 18 | 19.7 | [9 empty] | 0
Schedule 18 | 19.8 | [9 empty] | 0
Schedule 18 | 19.9 | [9 empty] | 0
Schedule 18 | 19.1 | [9 empty] | 0
Schedule 18 | 19.11 | [9 empty] | 0
Schedule 18 | 20 | [9 empty] | 0
Schedule 18 | 20.1 | [9 empty] | 0
Schedule 18 | 20.2 | [9 empty] | 0
Schedule 18 | 20.3 | [9 empty] | 0
Schedule 18 | 20.4 | [9 empty] | 0
Schedule 18 | 20.5 | [9 empty] | 0
Schedule 18 | 20.6 | [6 empty] | YES |  |  | 1
Schedule 18 | 20.7 | [6 empty] | YES |  |  | 1
Schedule 18 | 20.8 | [9 empty] | 0
Schedule 18 | 20.9 | [6 empty] | YES |  |  | 1
Schedule 18 | 21 | [9 empty] | 0
Schedule 18 | 21.1 | [9 empty] | 0
Schedule 18 | 21.2 | [9 empty] | 0
Schedule 18 | 22 | [9 empty] | 0
Schedule 18 | 22.1 | [9 empty] | 0
Schedule 18 | 22.2 | [9 empty] | 0
Schedule 18 | 22.3 | [9 empty] | 0
Schedule 18 | 22.4 | [9 empty] | 0
Schedule 18 | 23 | [9 empty] | 0
Schedule 18 | 23.1 | [9 empty] | 0
Schedule 18 | 23.2 | [9 empty] | 0
Schedule 18 | 23.3 | [9 empty] | 0
Schedule 18 | 23.4 | [9 empty] | 0
Schedule 18 | 23.5 | [9 empty] | 0
Schedule 18 | 24 | [9 empty] | 0
Schedule 18 | 24.1 | [9 empty] | 0
Schedule 18 | 24.2 | [9 empty] | 0
Schedule 18 | 24.3 | [9 empty] | 0
Schedule 18 | 24.4 | [9 empty] | 0
Schedule 18 | 24.5 | [9 empty] | 0
Schedule 18 | 24.6 | [9 empty] | 0
Schedule 18 | 24.7 | [9 empty] | 0
Schedule 18 | 24.8 | [9 empty] | 0
Schedule 18 | 24.9 | [9 empty] | 0
Schedule 18 | 25 | [9 empty] | 0
Schedule 18 | 25.1 | [9 empty] | 0
Schedule 18 | 25.2 | [9 empty] | 0
Schedule 18 | 25.3 | [9 empty] | 0
Schedule 18 | 25.4 | [9 empty] | 0
Schedule 18 | 25.5 | [9 empty] | 0
Schedule 18 | 25.6 | [9 empty] | 0
Schedule 18 | 25.7 | [9 empty] | 0
Schedule 18 | 25.8 | [9 empty] | 0
Schedule 18 | 25.9 | [9 empty] | 0
Schedule 18 | 25.1 | [9 empty] | 0
Schedule 18 | 25.11 | [9 empty] | 0
Schedule 18 | 25.12 | [9 empty] | 0
Schedule 18 | 25.13 | [9 empty] | 0
Schedule 18 | 25.14 | [9 empty] | 0
Schedule 18 | 25.15 | [9 empty] | 0
Schedule 18 | 25.16 | [9 empty] | 0
Schedule 18 | 25.17 | [9 empty] | 0
Schedule 18 | 25.18 | [9 empty] | 0
Schedule 18 | 25.19 | [9 empty] | 0
Schedule 18 | 26 | [9 empty] | 0
Schedule 18 | 26.1 | [9 empty] | 0
Schedule 18 | 26.2 | [9 empty] | 0
Schedule 18 | 26.3 | [9 empty] | 0
Schedule 18 | 26.4 | [9 empty] | 0
Schedule 18 | 26.5 | [9 empty] | 0
Schedule 18 | 26.6 | [9 empty] | 0
Schedule 18 | 26.7 | [9 empty] | 0
Schedule 18 | 26.8 | [9 empty] | 0
Schedule 18 | 26.9 | [9 empty] | 0
Schedule 18 | 26.1 | [9 empty] | 0
Schedule 18 | 26.11 | [9 empty] | 0
Schedule 18 | 27 | [9 empty] | 0
Schedule 18 | 27.1 | [9 empty] | 0
Schedule 18 | 27.2 | [9 empty] | 0
Schedule 18 | 27.3 | [9 empty] | 0
Schedule 18 | 27.4 | [9 empty] | 0
Schedule 18 | 28 | [9 empty] | 0
Schedule 18 | 28.1 | [9 empty] | 0
Schedule 18 | 28.2 | [9 empty] | 0
Schedule 18 | 29 | [9 empty] | 0
Schedule 18 | 29.1 | [9 empty] | 0
Schedule 18 | 29.2 | [9 empty] | 0
Schedule 18 | 29.3 | [9 empty] | 0
Schedule 18 | 29.4 | [9 empty] | 0
Schedule 18 | 30 | [9 empty] | 0
Schedule 18 | 30.1 | [9 empty] | 0
Schedule 18 | 30.2 | [9 empty] | 0
Schedule 18 | 30.3 | [9 empty] | 0
Schedule 18 | 30.4 | [9 empty] | 0
Schedule 18 | 30.5 | [9 empty] | 0
Schedule 18 | 30.6 | [9 empty] | 0
Schedule 18 | 30.7 | [9 empty] | 0
Schedule 18 | 30.8 | [9 empty] | 0
Schedule 18 | 30.9 | [9 empty] | 0
Schedule 18 | 30.1 | [9 empty] | 0
Schedule 18 | 30.11 | [9 empty] | 0
Schedule 18 | 31 | [9 empty] | 0 | DCP 439 Introduces new Paragraph 31
Schedule 18 | 31.1 | [9 empty] | 0 | DCP 439 Introduces new Paragraph 31.1
Schedule 18: Annex 1 | 1 | [9 empty] | 0
Schedule 18: Annex 1 | 1.1 | [9 empty] | 0
Schedule 18: Annex 1 | 2 | [9 empty] | 0
Schedule 18: Annex 1 | 2.1 | [9 empty] | 0
Schedule 18: Annex 1 | 2.2 | [9 empty] | 0
Schedule 18: Annex 1 | 2.3 | [9 empty] | 0
Schedule 18: Annex 1 | 2.4 | [9 empty] | 0
Schedule 18: Annex 1 | 2.5 | [9 empty] | 0
Schedule 18: Annex 1 | 3 | [9 empty] | 0
Schedule 18: Annex 1 | Definitions | [9 empty] | 0
Schedule 18: Annex 1 | 4 | [9 empty] | 0
Schedule 18: Annex 1 | 4.1 | [9 empty] | 0
Schedule 18: Annex 1 | 4.2 | [9 empty] | 0
Schedule 18: Annex 1 | 4.3 | [9 empty] | 0
Schedule 18: Annex 1 | 4.4 | [9 empty] | 0
Schedule 18: Annex 1 | 4.5 | [9 empty] | 0
Schedule 18: Annex 1 | 4.6 | [9 empty] | 0
Schedule 18: Annex 1 | 4.7 | [9 empty] | 0
Schedule 18: Annex 1 | 4.8 | [9 empty] | 0
Schedule 18: Annex 1 | 4.9 | [9 empty] | 0
Schedule 18: Annex 1 | 5 | [9 empty] | 0
Schedule 18: Annex 1 | 5.1 | [9 empty] | 0
Schedule 18: Annex 1 | 5.2 | [9 empty] | 0
Schedule 18: Annex 1 | 5.3 | [9 empty] | 0
Schedule 18: Annex 1 | 5.4 | [9 empty] | 0
Schedule 18: Annex 1 | 5.5 | [9 empty] | 0
Schedule 18: Annex 1 | 5.6 | [9 empty] | 0
Schedule 18: Annex 1 | 5.7 | [9 empty] | 0
Schedule 18: Annex 1 | 5.8 | [9 empty] | 0
Schedule 18: Annex 1 | 5.9 | [9 empty] | 0
Schedule 18: Annex 1 | 5.1 | [9 empty] | 0
Schedule 18: Annex 1 | 5.11 | [9 empty] | 0
Schedule 18: Annex 1 | 5.12 | [9 empty] | 0
Schedule 18: Annex 1 | 5.13 | [9 empty] | 0
Schedule 18: Annex 1 | 5.14 | [9 empty] | 0
Schedule 18: Annex 1 | 5.15 | [9 empty] | 0
Schedule 18: Annex 1 | 5.16 | [9 empty] | 0
Schedule 18: Annex 1 | 5.17 | [9 empty] | 0
Schedule 18: Annex 1 | 5.18 | [9 empty] | 0
Schedule 18: Annex 1 | 5.19 | [9 empty] | 0
Schedule 18: Annex 1 | 5.2 | [9 empty] | 0
Schedule 18: Annex 1 | 5.21 | [9 empty] | 0
Schedule 18: Annex 1 | 5.22 | [9 empty] | 0
Schedule 18: Annex 1 | 5.23 | [9 empty] | 0
Schedule 18: Annex 1 | 5.24 | [9 empty] | 0
Schedule 18: Annex 1 | 5.25 | [9 empty] | 0
Schedule 18: Annex 1 | 5.26 | [9 empty] | 0
Schedule 18: Annex 1 | 5.27 | [9 empty] | 0
Schedule 18: Annex 1 | 5.28 | [9 empty] | 0
Schedule 18: Annex 1 | 5.29 | [9 empty] | 0
Schedule 18: Annex 1 | 5.3 | [9 empty] | 0
Schedule 18: Annex 1 | 5.31 | [9 empty] | 0
Schedule 18: Annex 1 | 5.32 | [9 empty] | 0
Schedule 18: Annex 1 | 5.33 | [9 empty] | 0
Schedule 18: Annex 1 | 5.34 | [9 empty] | 0
Schedule 18: Annex 1 | 5.35 | [9 empty] | 0
Schedule 18: Annex 1 | 5.36 | [9 empty] | 0
Schedule 18: Annex 1 | 5.37 | [9 empty] | 0
Schedule 18: Annex 1 | 5.38 | [9 empty] | 0
Schedule 18: Annex 1 | 5.39 | [9 empty] | 0
Schedule 18: Annex 1 | 5.4 | [9 empty] | 0
Schedule 18: Annex 1 | 5.41 | [9 empty] | 0
Schedule 18: Annex 1 | 5.42 | [9 empty] | 0
Schedule 18: Annex 1 | 6 | [9 empty] | 0
Schedule 18: Annex 1 | 6.1 | [9 empty] | 0
Schedule 18: Annex 1 | 6.2 | [9 empty] | 0
Schedule 18: Annex 1 | 6.3 | [9 empty] | 0
Schedule 18: Annex 1 | 6.4 | [9 empty] | 0
Schedule 18: Annex 1 | 6.5 | [9 empty] | 0
Schedule 18: Annex 1 | 6.6 | [9 empty] | 0
Schedule 18: Annex 1 | 6.7 | [9 empty] | 0
Schedule 18: Annex 1 | 6.8 | [9 empty] | 0
Schedule 18: Annex 1 | 6.9 | [9 empty] | 0
Schedule 18: Annex 1 | 6.1 | [9 empty] | 0
Schedule 18: Annex 1 | 6.11 | [9 empty] | 0
Schedule 18: Annex 1 | 6.12 | [9 empty] | 0
Schedule 18: Annex 1 | 6.13 | [9 empty] | 0
Schedule 18: Annex 1 | 6.14 | [9 empty] | 0
Schedule 18: Annex 1 | 6.15 | [9 empty] | 0
Schedule 18: Annex 1 | 6.16 | [9 empty] | 0
Schedule 18: Annex 1 | 6.17 | [9 empty] | 0
Schedule 18: Annex 1 | 6.18 | [9 empty] | 0
Schedule 18: Annex 1 | 6.19 | [9 empty] | 0
Schedule 18: Annex 1 | 6.2 | [9 empty] | 0
Schedule 18: Annex 1 | 6.21 | [9 empty] | 0
Schedule 18: Annex 1 | 6.22 | [9 empty] | 0
Schedule 18: Annex 1 | 6.23 | [9 empty] | 0
Schedule 18: Annex 1 | 6.24 | [9 empty] | 0
Schedule 18: Annex 1 | 6.25 | [9 empty] | 0
Schedule 18: Annex 1 | 6.26 | [9 empty] | 0
Schedule 18: Annex 1 | 6.27 | [9 empty] | 0
Schedule 18: Annex 1 | 6.28 | [9 empty] | 0
Schedule 18: Annex 1 | 6.29 | [9 empty] | 0
Schedule 18: Annex 1 | 6.3 | [9 empty] | 0
Schedule 18: Annex 1 | 6.31 | [9 empty] | 0
Schedule 18: Annex 1 | 6.32 | [9 empty] | 0
Schedule 18: Annex 1 | 6.33 | [9 empty] | 0
Schedule 18: Annex 1 | 6.34 | [9 empty] | 0
Schedule 18: Annex 1 | 7 | [9 empty] | 0
Schedule 18: Annex 1 | 7.1 | [9 empty] | 0
Schedule 18: Annex 1 | 7.2 | [9 empty] | 0
Schedule 18: Annex 1 | 7.3 | [9 empty] | 0
Schedule 18: Annex 1 | 7.4 | [9 empty] | 0
Schedule 18: Annex 1 | 7.5 | [9 empty] | 0
Schedule 18: Annex 1 | 8 | [9 empty] | 0
Schedule 18: Annex 1 | 8.1 | [9 empty] | 0
Schedule 18: Annex 1 | 8.2 | [9 empty] | 0
Schedule 18: Annex 1 | 8.3 | [9 empty] | 0
Schedule 18: Annex 1 | 8.4 | [9 empty] | 0
Schedule 18: Annex 1 | 8.5 | [9 empty] | 0
Schedule 18: Annex 1 | 8.6 | [9 empty] | 0
Schedule 18: Annex 1 | 8.7 | [9 empty] | 0
Schedule 18: Annex 1 | 8.8 | [9 empty] | 0
Schedule 18: Annex 1 | 8.9 | [9 empty] | 0
Schedule 18: Annex 1 | 8.1 | [9 empty] | 0
Schedule 18: Annex 1 | 8.11 | [9 empty] | 0
Schedule 18: Annex 1 | 8.12 | [9 empty] | 0
Schedule 18: Annex 1 | 8.13 | [9 empty] | 0
Schedule 18: Annex 1 | 8.14 | [9 empty] | 0
Schedule 18: Annex 1 | 8.15 | [9 empty] | 0
Schedule 18: Annex 1 | 8.16 | [9 empty] | 0
Schedule 18: Annex 1 | 8.17 | [9 empty] | 0
Schedule 18: Annex 1 | 8.18 | [9 empty] | 0
Schedule 18: Annex 1 | 8.19 | [9 empty] | 0
Schedule 18: Annex 1 | 8.2 | [9 empty] | 0
Schedule 18: Annex 1 | 8.21 | [9 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [9 empty] | 0
Schedule 18: Annex 1 | Attachment 2 | [9 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [9 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [9 empty] | 0
0
Schedule 20 | Introduction | [9 empty] | 0
Schedule 20 | 1.1 | [9 empty] | 0
Schedule 20 | 2.1 | [9 empty] | 0
Schedule 20 | 3.1 | [9 empty] | 0
Schedule 20 | 3.2 | [9 empty] | 0
0
Schedule 29 | Introduction | [9 empty] | 0
Schedule 29 | 1 | [9 empty] | 0
Schedule 29 | 1A | [9 empty] | 0
Schedule 29 | 2 | [9 empty] | 0
Schedule 29 | 3 | [9 empty] | 0
Schedule 29 | 4 | [9 empty] | 0
Schedule 29 | 5 | [9 empty] | 0
Schedule 29 | 6 | [9 empty] | 0
Schedule 29 | 7 | [9 empty] | 0
Schedule 29 | 8 | [9 empty] | 0
Schedule 29 | 9 | [9 empty] | 0
Schedule 29 | 10 | [9 empty] | 0
Schedule 29 | 11 | [9 empty] | 0
Schedule 29 | 11A | [9 empty] | 0
Schedule 29 | 12 | [9 empty] | 0
Schedule 29 | 13 | [9 empty] | 0
Schedule 29 | 14 | [9 empty] | 0
Schedule 29 | 15 | [9 empty] | 0
Schedule 29 | 16 | [9 empty] | 0
Schedule 29 | 17 | [9 empty] | 0
Schedule 29 | 18 | [9 empty] | 0
Schedule 29 | 19 | [9 empty] | 0
Schedule 29 | 20 | [9 empty] | 0
Schedule 29 | 21 | [9 empty] | 0
Schedule 29 | 22 | [9 empty] | 0
Schedule 29 | 23 | [9 empty] | 0
Schedule 29 | 24 | [9 empty] | 0
Schedule 29 | 25 | [9 empty] | 0
Schedule 29 | 26 | [9 empty] | 0
Schedule 29 | 27 | [9 empty] | 0
Schedule 29 | 28 | [9 empty] | 0
Schedule 29 | 29 | [9 empty] | 0
Schedule 29 | 30 | [9 empty] | 0
Schedule 29 | 31 | [9 empty] | 0
Schedule 29 | 32 | [9 empty] | 0
Schedule 29 | 33 | [9 empty] | 0
Schedule 29 | 34 | [9 empty] | 0
Schedule 29 | 35 | [9 empty] | 0
Schedule 29 | 36 | [9 empty] | 0
Schedule 29 | 37 | [9 empty] | 0
Schedule 29 | 38 | [9 empty] | 0
Schedule 29 | 39 | [9 empty] | 0
Schedule 29 | 40 | [9 empty] | 0
Schedule 29 | 41 | [9 empty] | 0
Schedule 29 | 42 | [9 empty] | 0
Schedule 29 | 43 | [9 empty] | 0
Schedule 29 | 44 | [9 empty] | 0
Schedule 29 | 45 | [9 empty] | 0
Schedule 29 | 46 | [9 empty] | 0
Schedule 29 | 46A | [9 empty] | 0
Schedule 29 | 47 | [9 empty] | 0
0
Schedule 32 | 1 | [9 empty] | 0
Schedule 32 | 1.1 | [9 empty] | 0
Schedule 32 | 1.2 | [9 empty] | 0
Schedule 32 | 1.2A | [9 empty] | 0
Schedule 32 | 1.3 | [9 empty] | 0
Schedule 32 | 1.4 | [9 empty] | 0
Schedule 32 | 1.5 | [9 empty] | 0
Schedule 32 | 1.6 | [9 empty] | 0
Schedule 32 | 1.7 | [9 empty] | 0
Schedule 32 | 1.8 |  | YES | [7 empty] | 1
Schedule 32 | 1.9 | [9 empty] | 0
Schedule 32 | 1.10 |  | YES | [7 empty] | 1
Schedule 32 | 2 | [9 empty] | 0
Schedule 32 | 2.1 | [9 empty] | 0
Schedule 32 | 2.2 | [9 empty] | 0
Schedule 32 | 2.3 | [9 empty] | 0
Schedule 32 | 2.4 | [9 empty] | 0
Schedule 32 | 2.5 | [9 empty] | 0
Schedule 32 | 3 | [9 empty] | 0
Schedule 32 | 3.1 |  | YES | [7 empty] | 1
Schedule 32 | 3.2 | [9 empty] | 0
Schedule 32 | 3.3 | [9 empty] | 0
Schedule 32 | 3.4 | [9 empty] | 0
Schedule 32 | 3.5 | [9 empty] | 0
Schedule 32 | 3.6 | [9 empty] | 0
Schedule 32 | 4 | [9 empty] | 0
Schedule 32 | 4.1 |  | YES | [7 empty] | 1
Schedule 32 | 4.2 |  | YES | [7 empty] | 1
Schedule 32 | 4.2A |  | YES | [7 empty] | 1
Schedule 32 | 4.3 | [9 empty] | 0
Schedule 32 | 4.4 | [9 empty] | 0
Schedule 32 | 4.5 |  | YES | [7 empty] | 1
Schedule 32 | 4.6 | [9 empty] | 0
Schedule 32 | 5 | [9 empty] | 0
Schedule 32 | 5.1 | [9 empty] | 0
Schedule 32 | 5.2 | [9 empty] | 0
Schedule 32 | 5.3 | [9 empty] | 0
Schedule 32 | 5A. |  | YES | [7 empty] | 1
Schedule 32 | 5A.1 | [9 empty] | 0
Schedule 32 | 5A.1A | [9 empty] | 0
Schedule 32 | 5A.2 | [9 empty] | 0
Schedule 32 | 6 | [9 empty] | 0
Schedule 32 | 6.1 |  |  | YES | [6 empty] | 1
Schedule 32 | 6.2 |  |  | YES | [6 empty] | 1
Schedule 32 | 6.3 |  | YES | [7 empty] | 1
Schedule 32 | 6.4 | [9 empty] | 0
Schedule 32 | 6.4A | [9 empty] | 0
Schedule 32 | 6.5 |  | YES | [7 empty] | 1
Schedule 32 | 6.6 | [9 empty] | 0
Schedule 32 | 6.7 | [9 empty] | 0
Schedule 32 | 6.8 | [9 empty] | 0
Schedule 32 | 6.9 | [9 empty] | 0
Schedule 32 | 6.10 | [9 empty] | 0
Schedule 32 | 6.11 | [9 empty] | 0
Schedule 32 | 6.12 | [9 empty] | 0
Schedule 32 | 7 | [9 empty] | 0
Schedule 32 | 7.1 | [9 empty] | 0
Schedule 32 | 7.2 | [9 empty] | 0
Schedule 32 | 7.3 | [9 empty] | 0
Schedule 32 | 7.4 | [9 empty] | 0
Schedule 32 | 7.5 | [9 empty] | 0
Schedule 32 | 7.6 | [9 empty] | 0
Schedule 32 | 7.7 | [9 empty] | 0
Schedule 32 | 7.8 | [9 empty] | 0
Schedule 32 | 7.9 | [9 empty] | 0
Schedule 32 | 7.1 | [9 empty] | 0
Schedule 32 | 7.11 | [9 empty] | 0
Schedule 32 | 7.12 | [9 empty] | 0
Schedule 32 | 7.13 | [9 empty] | 0
Schedule 32 | 7.14 | [9 empty] | 0
Schedule 32 | 7.15 | [9 empty] | 0
Schedule 32 | 7.16 | [9 empty] | 0
Schedule 32 | 7.17 | [9 empty] | 0
Schedule 32 | 8 | [9 empty] | 0
Schedule 32 | 8.1 | [9 empty] | 0
Schedule 32 | 8.2 | [9 empty] | 0
Schedule 32 | Definitions |  | YES | YES | [6 empty] | 2
Charging Methodology CPs Legal Text Overlap Tracker