## DCUSA Issues Log
Column1 | Issue Name | Status | Status Last Changed | Proposer | Outcome
DIF 91 | Notices Under NTC | Open | 2026-07-15 | Peter Waymont | New issue
DIF 90 | DCP414/458 Guidance – DNO contact details | Closed | 2026-05-15 | Urszula Thorpe | Closed after agreeing to raise the obligations at the monthly IDNO forum and will revisit again in August to check that the data/contact details are being shared.
DIF 89 | D0164 / MM00069 Flows | Closed | 2025-10-29 | Mark Bellman | Proposer has agreed to raise a CP for this.
DIF 88 | Excess capacity calculation carried out in Durabill when an MPAN changes supplier | Open | 2025-08-29 | Emma Clarke | Proposer to consider the advice from SIG on the potential solution further and report back to SIG.
DIF 87 | Chages #2 | Closed | 2025-07-18 | Peter Waymont | This issue has been closed after the RFI responses were reviewed.
DIF 86 | Charges #1 | Closed | 2025-07-18 | Peter Waymont | This issue has been closed after the RFI responses were reviewed.
DIF 85 | Housekeeping item 123- Updates to company names in Section 3 of Schedule 2B and Schedules 17 and 18 | Closed | 2025-07-18 | Andy Green | Closed as agreed to raise a CP
DIF 84 | House Keeping Item 123-'Consequential changes as a result of Distribution Code Review Panel (DCRP) DCRP/18/03 and DCRP/MP/19/02' | Closed | 2025-07-18 | Andy Green | Closed as agreed to raise a CP
DIF 83 | Housekeeping Log Update via a CP | Closed | 2025-06-27 | Andy Green | Closed as several of the items will be remedied within DCP 457 and the other items are to be discussed at the July SIG meeting as part of DIFs 84 and 85
DIF 82 | How IDNOs are invoiced DUoS by host DNO | Closed | 2025-05-27 | Anne‑Claire Leydier | Closed as CP has been raised.
DIF 81 | Making RAV uplift consistent with PCFM inflation basis | Closed | 2025-04-16 | Mark Bellman | To be discussed at the April SIG
DIF 80 | DE-Energised Sites | Closed | 2025-03-21 | Peter Waymont | Closed as SIG has investigated and issue raiser to consider options.
DIF 79 | Credit Cover Clarifications | Closed | 2025-02-21 | Mark Bellman | Closed. Issue propser to raise a DCUSA change proposal
DIF 78 | Use of Genorators | Closed | 2025-02-21 | Komal Brown | Closed as the REC are completing an end to end review of the new connections process which will now include the use/installations of generators.
DIF 77 | Meter Bypass Notification Process | Open | 2025-02-21 | Komal Brown | Doodle Polls issued to agree next meeting date. High level process steps doc created
DIF 76 | MPAN and GSP group correction and charges | Closed | 2025-02-21 | Komal Brown | Closed as the issue may be part of a wider list of issues that the issue raiser is considering raising a new DIF to tackle.
DIF 75 | DCP414 - Transitional Protection for NHH CT Customers affected by regulatory change | Closed | 2024-07-09 | Rachel Wallace | This issue has been closed as a new DCP is to bn raised by the issue raiser.
DIF 74 | Super Customer Invoicing Issues | Closed | 2024-04-26 | Kevin Wollard | Was discussed at Aprils SIG and issue closed as the its believed the benefit of making a change would be outweighed eighted by the costs of making billing system and process changes.
DIF 73 | Increase the number of allowed alternatives | Closed | 2024-03-22 | Simon Vicary | This issue has been closed as a new DCP has been raised.
DIF 72 | Moving Meters | Open | 2024-01-12 | Peter Waymont | RFI has taken place and the SIG agreed to review the responses in a sub group on 05 February 2024.
DIF 71 | Use of Genorators | Closed | 2024-01-12 | Komal Brown | Closed as the issue proposer has advised a new Dif is to be raised after reading the RFI responses
DIF 70 | Legal Meter Bypass | Closed | 2024-01-12 | Komal Brown | Closed as the issue proposer has advised a new Dif is to be raised after reading the RFI responses
DIF 69 | Inocrrect GSP | Closed | 2024-01-12 | Komal Brown | Closed as the issue proposer has advised a new Dif is to be raised after reading the RFI responses
DIF 68 | Reducing Good Payment Record | Closed | 2023-08-25 | Peter Waymont | SIG agreed to raise a new change propasol to remedy the issue
DIF 67 | Use of "REP-242” in aggregated billing | Closed | 2023-07-14 | Peter Waymont | Consultation has taken place and the SIG agreed to raise a new change propsal to remedy the issue.
DIF 66 | Lead Times for approved DCPs Requiring System Changes for Implementation | Closed | 2023-04-20 | Chrisy Austin | A CP has been raised and therefore this issues has been closed.
DIF 65 | 200Amp Fuses with Lower-Rted Tails | Closed | 2023-04-20 | Carl Dennis | The Secretariat has published guidance on the DCUSA website in relation to data flow development and lead time for implementation.
DIF 64 | DCUSA Schedule 8, Para 13 Obligations - Rota Load Block Alpha Identifiers | Open | 2023-04-20 | Garth Graham | This issue has been progressed to a SIG Sub0Group (DIF 64) and may need to be reconvened shortly for further discussion.
DIF 63 | Provision of a Supplier Emergency 24/7 Metering Service | Closed | 2022-04-22 | Chrisy Austin | Closed.
DIF 62 | Additional Clarification for correct application of the LV Sub Site Specific Tariff | Closed | 2022-01-12 | Donna Townsend | It was agreed at the SIG meeting on 25 February that this issue should be considered further via a DIF 62 Sub-Group.
DIF 61 | Anti-competitive charging of Third Party DNO works to transmission connecter users | Closed | 2021-02-26 | Mikey Clark Maddie Brooks Charles Deacon | After discussion at the SIG meeting held on 26 February 2021, it was agreed that EDF would raise a DCUSA Change Proposal regarding this issue.
DIF 60 | DNO Emergency prepayment meter (PPM) top-up vouchers for vulnerable customers | Closed | 2020-07-31 | Andrew Sherry | Not progressed further through DCUSA.
DIF 59 | Network operator ability to manage consumer devices (such as EV chargers) connected to Smart Meter infrastructure to prevent network overloads in emergency scenarios | Closed | 2020-05-21 | Richard Hartshorn | Progressed to Change Proposal (DCP 371).
DIF 58 | Suppliers Payment Terms and Cover calculations during COVID-19 pandemic | Closed | 2020-04-24 | Garry Pickering | After discussion there was a general view that there is a need for a more holistic approach to this issue and perhaps a dual fuel solution. Members were keen to understand if Ofgem is considering a wider industry approach.
DIF 57 | Effectiveness of the current provision of unsecured cover | Closed | 2019-07-12 | Andrew Sherry | Progressed to Change Proposal (DCP 349).
DIF 56 | Double voting rights within DCUSA | Closed | 2019-02-15 | DCP 295 WG/ DCUSA Panel | The SIG concluded that DIF 56 should not progress further at this stage, however the Secretariat should review any future instances where a party votes in more than one party category to analyse whether this has had an effect on the overall result and decide whether this issue needs to be revisited as appropriate.
DIF 55 | Rota disconnections DVD | Closed | 2018-10-19 | Peter Waymont | It was agreed that Peter Waymont would progress this to a Change Proposal, pending reviwing exisiting contractual obligations.
DIF 54 | Billing and Remittance via data flow | Closed | 2018-07-27 | Claire Towler | The DCUSA SIG considered this issue at the 27 July 2018 meeting. The proposer has agreed to draft a Change Proposal using the guidence recieved during SIG meeting.
DIF 53 | National Terms of Connection (NToC) - De-Energisation | Closed | 2018-07-27 | David Spillet | The DCUSA SIG considered this issue at the 27 July 2018 meeting. The proposer has agreed to draft a Change Proposal using the guidence recieved during SIG meeting.
DIF 52 | Operational Contacts | Closed | 2017-09-29 | Warren Lacey | It was noted that the MOCOPA review panel has met and will be putting an operational contacts list together. It was further noted that Energy UK currently have a list, however, the list is voluntary and only consists members who have opted in. Northern Powergrid are exploring ways for the list to be kept up to date on a more rigid basis. Northern Powergrid intends to raise a change through MOCOPA. Updates will be provided when they arrise.
DIF 51 | Letters Of Credit and Bank Credit Ratings’ | Closed | 2017-09-29 | Peter Waymont | BEIS and the British Banking Association approached the DCUSA in relation to its out of date credit cover arrangements which do not reflect the current economic environment. The RFI responses broadly agreed that credit cover arrangments should be relaxed, more detail can be found in September 2017 minutes. It is now up to DCUSA Parties to raise a CP.
DIF 50 | RTS Management in SMETS2 | Closed | 2016-05-27 | Emslie Law | A subgroup to the DCUSA SIG was set up comprising of industry experts to consider Load Managed Areas (LMAs) and the rest of the energy industry where the primary function of RTS is switching. This group were awaiting the outcome of an ENA consultation on the same topic before proceeding to consultaiton or RFI. ElectraLink will contact the ENA regarding the consultation.